## LABOR PRODUCTIVITY
ACTIVITIES |  | OUTPUT PER HOUR | [5 empty] | MANHOUR EQUIVALENT
[8 empty] | 58.6806 | per hour in area of CAR
EQUIVALENT LABOR COST
ITEM NO. | WORK DESCRIPTION | 3 WORKER PRODUCTIVITY RATE
|  | SLOW | UNIT | AVERAGE | UNIT | FAST | UNIT | SLOW | PESOS PER | AVERAGE | PESOS PER | FAST | PESOS PER
A. | FORM WORKS INSTALLATION
| WALL ON THE GROUND | 0.25 | SQ.M.per hour | 0.5 | SQ.M.per hour | 0.625 | SQ.M.per hour | 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M.
| WALL ABOVER GROUND | 0.21277 | SQ.M.per hour | 0.42553 | SQ.M.per hour | 0.53191 | SQ.M.per hour | 275.7986 | per SQ.M. | 137.8993 | per SQ.M. | 110.3194 | per SQ.M.
| BEAMS | 0.16234 | SQ.M.per hour | 0.32468 | SQ.M.per hour | 0.4065 | SQ.M.per hour | 361.4722 | per SQ.M. | 180.7361 | per SQ.M. | 144.3542 | per SQ.M.
| COLUMN | 0.21277 | SQ.M.per hour | 0.42553 | SQ.M.per hour | 0.53191 | SQ.M.per hour | 275.7986 | per SQ.M. | 137.8993 | per SQ.M. | 110.3194 | per SQ.M.
| SUSPENDED SLAB | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 0 TO 18' | 0.2994 | SQ.M.per hour | 0.5988 | SQ.M.per hour | 0.74627 | SQ.M.per hour | 195.9931 | per SQ.M. | 97.9965 | per SQ.M. | 78.6319 | per SQ.M.
| 18' TO 36' UP | 0.15015 | SQ.M.per hour | 0.3003 | SQ.M.per hour | 0.37594 | SQ.M.per hour | 390.8125 | per SQ.M. | 195.4062 | per SQ.M. | 156.0903 | per SQ.M.
| ELEVATED AND SHORED SLAB FORMING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FORMING ONLY | 0.05814 | SQ.M.per hour | 0.11111 | SQ.M.per hour | 0.14535 | SQ.M.per hour | 1009.3056 | per SQ.M. | 528.125 | per SQ.M. | 403.7222 | per SQ.M.
| FORMING AND SHORING | 0.045455 | SQ.M.per hour | 0.090909 | SQ.M.per hour | 0.11364 | SQ.M.per hour | 1290.9722 | per SQ.M. | 645.4861 | per SQ.M. | 516.3889 | per SQ.M.
| WOOD WALL AND PARTITION | 1 | SQ.M.per hour | 1.6667 | SQ.M.per hour | 2.5 | SQ.M.per hour | 58.6806 | per SQ.M. | 35.2083 | per SQ.M. | 23.4722 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
B. | FORMWORKS FABRICATION | 0.46512 | SQ.M.per hour | 0.92593 | SQ.M.per hour | 1.1628 | SQ.M.per hour | 126.1632 | per SQ.M. | 63.375 | per SQ.M. | 50.4653 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
C. | STRIPPING OF FORMS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WALL ON GROUND | 2 | SQ.M.per hour | 4 | SQ.M.per hour | 5 | SQ.M.per hour | 29.3403 | per SQ.M. | 14.6701 | per SQ.M. | 11.7361 | per SQ.M.
| WALL ABOVE 10' | 0.3876 | SQ.M.per hour | 0.77519 | SQ.M.per hour | 0.97087 | SQ.M.per hour | 151.3958 | per SQ.M. | 75.6979 | per SQ.M. | 60.441 | per SQ.M.
| BEAMS | 0.48544 | SQ.M.per hour | 0.97087 | SQ.M.per hour | 1.2195 | SQ.M.per hour | 120.8819 | per SQ.M. | 60.441 | per SQ.M. | 48.1181 | per SQ.M.
| COLUMNS | 0.58824 | SQ.M.per hour | 1.1765 | SQ.M.per hour | 1.4706 | SQ.M.per hour | 99.7569 | per SQ.M. | 49.8785 | per SQ.M. | 39.9028 | per SQ.M.
| SUSPENDED SLAB | 0 | SQ.M.per hour | 0 | SQ.M.per hour | 0 | SQ.M.per hour | 0 | per SQ.M. | 0 | per SQ.M. | 0 | per SQ.M.
| 0 TO 18' | 0.5988 | SQ.M.per hour | 1.2048 | SQ.M.per hour | 1.4925 | SQ.M.per hour | 97.9965 | per SQ.M. | 48.7049 | per SQ.M. | 39.316 | per SQ.M.
| 18' TO 36' UP | 0.46296 | SQ.M.per hour | 0.92593 | SQ.M.per hour | 1.1628 | SQ.M.per hour | 126.75 | per SQ.M. | 63.375 | per SQ.M. | 50.4653 | per SQ.M.
| ELEVATED AND SHORED SLAB FORMING | 0 | SQ.M.per hour | 0 | SQ.M.per hour | 0 | SQ.M.per hour | 0 | per SQ.M. | 0 | per SQ.M. | 0 | per SQ.M.
| STRIP OF FORMS | 0.14286 | SQ.M.per hour | 0.28571 | SQ.M.per hour | 0.35714 | SQ.M.per hour | 410.7639 | per SQ.M. | 205.3819 | per SQ.M. | 164.3056 | per SQ.M.
| FLOOR SLAB AT GRADE STRIP OF FORMS | 0.17857 | SQ.M.per hour | 0.35714 | SQ.M.per hour | 0.44643 | SQ.M.per hour | 328.6111 | per SQ.M. | 164.3056 | per SQ.M. |  | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
D | INSTALLION OF CARPENTRY WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PLYWOOD PARTITION | 0.5 | PCper hour | 1 | PCper hour | 1.25 | PCper hour | 117.3611 | per PC | 58.6806 | per PC | 46.9444 | per PC
| T & G FLOORING AND SHORING | 3.4483 | B.F.per hour | 7.1429 | B.F.per hour | 9.0909 | B.F.per hour | 17.0174 | per B.F. | 8.2153 | per B.F. | 6.4549 | per B.F.
| CEILING FRAME | 3.3333 | B.F.per hour | 2.7778 | B.F.per hour | 3.4483 | B.F.per hour | 17.6042 | per B.F. | 21.125 | per B.F. | 17.0174 | per B.F.
| SIDING FRAME | 1.8868 | B.F.per hour | 3.7037 | B.F.per hour | 4.7619 | B.F.per hour | 31.1007 | per B.F. | 15.8438 | per B.F. | 12.3229 | per B.F.
| FLOORING FRAME | 0.51546 | B.F.per hour | 1.0309 | B.F.per hour | 1.2987 | B.F.per hour | 113.8403 | per B.F. | 56.9201 | per B.F. | 45.184 | per B.F.
| WOODEN POSS ERECTION | 1.1765 | B.F.per hour | 2.3256 | B.F.per hour | 2.9412 | B.F.per hour | 49.8785 | per B.F. | 25.2326 | per B.F. | 19.9514 | per B.F.
| TRUSS FABRICATION | 1.4286 | B.F.per hour | 2.8571 | B.F.per hour | 3.5714 | B.F.per hour | 41.0764 | per B.F. | 20.5382 | per B.F. | 16.4306 | per B.F.
| TRUSS INSTALLATION | 0.625 | B.F.per hour | 1.25 | B.F.per hour | 1.5625 | B.F.per hour | 93.8889 | per B.F. | 46.9444 | per B.F. | 37.5556 | per B.F.
| GIRTS INSTALLTION | 2.3256 | B.F.per hour | 4.7619 | B.F.per hour | 5.8824 | B.F.per hour | 25.2326 | per B.F. | 12.3229 | per B.F. | 9.9757 | per B.F.
| PLATES INSTALLATION | 3.7037 | B.F.per hour | 7.6923 | B.F.per hour | 9.0909 | B.F.per hour | 15.8438 | per B.F. | 7.6285 | per B.F. | 6.4549 | per B.F.
| PURLINS INSTALLATION | 1.8868 | B.F.per hour | 3.7037 | B.F.per hour | 10 | B.F.per hour | 31.1007 | per B.F. | 15.8438 | per B.F. | 5.8681 | per B.F.
| FASCIA BOARD INSTALLATION | 1.0989 | B.F.per hour | 2.1739 | B.F.per hour | 2.7778 | B.F.per hour | 53.3993 | per B.F. | 26.9931 | per B.F. | 21.125 | per B.F.
| 1/4" or 3/4" thk PLYWOOD | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CUTTING BY MANUAL | 0.5 | PCper hour | 1 | PCper hour | 1.25 | PCper hour | 117.3611 | per PC | 58.6806 | per PC | 46.9444 | per PC
| ASSEMBLY | 1.2048 | S.F.per hour | 2.381 | S.F.per hour | 3.0303 | S.F.per hour | 48.7049 | per S.F. | 24.6458 | per S.F. | 19.3646 | per S.F.
| CEILNG: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FRAME INSTALLATION | 0.37594 | SQ.M.per hour | 0.75188 | SQ.M.per hour | 0.9434 | SQ.M.per hour | 156.0903 | per SQ.M. | 78.0451 | per SQ.M. | 62.2014 | per SQ.M.
| PLYWOOD INSTALLLATION | 0.5 | SQ.M.per hour | 1 | SQ.M.per hour | 1.1111 | SQ.M.per hour | 117.3611 | per SQ.M. | 58.6806 | per SQ.M. | 52.8125 | per SQ.M.
| CABINET BOARDING | 3.8462 | B.F.per hour | 7.6923 | B.F.per hour | 10 | B.F.per hour | 15.2569 | per B.F. | 7.6285 | per B.F. | 5.8681 | per B.F.
| CABINET FRAMING | 2.7778 | B.F.per hour | 5.5556 | B.F.per hour | 7.1429 | B.F.per hour | 21.125 | per B.F. | 10.5625 | per B.F. | 8.2153 | per B.F.
| WOOD WALL PARTITION | 1 | SQ.M.per hour | 2 | SQ.M.per hour | 2.5 | SQ.M.per hour | 58.6806 | per SQ.M. | 29.3403 | per SQ.M. | 23.4722 | per SQ.M.
| PANEL WALL | 0.071429 | SQ.M.per hour | 0.14286 | SQ.M.per hour | 0.17857 | SQ.M.per hour | 821.5278 | per SQ.M. | 410.7639 | per SQ.M. | 328.6111 | per SQ.M.
| FORMING WEIGHT ANCHOR BOLT | 0.11111 | SQ.M.per hour | 0.22222 | SQ.M.per hour | 0.27778 | SQ.M.per hour | 528.125 | per SQ.M. | 264.0625 | per SQ.M. | 211.25 | per SQ.M.
| WET FORMING | 0.14286 | SQ.M.per hour | 0.28571 | SQ.M.per hour | 0.35714 | SQ.M.per hour | 410.7639 | per SQ.M. | 205.3819 | per SQ.M. | 164.3056 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
E. | DOORS AND WINDOWS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| W-PANEL INSTALLATION | 1.25 | PC.per hour | 2.5 | PC.per hour | 3.125 | PC.per hour | 46.9444 | per PC. | 23.4722 | per PC. | 18.7778 | per PC.
| STEEL WINDOWS INSTALLATION | 0.25 | PC.per hour | 0.5 | PC.per hour | 0.625 | PC.per hour | 234.7222 | per PC. | 117.3611 | per PC. | 93.8889 | per PC.
| LOUVER WINDOWS INSTALLATION: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIXED ASBESTOS | 0.10799 | SQ.M.per hour | 0.21598 | SQ.M.per hour | 0.27027 | SQ.M.per hour | 543.3819 | per SQ.M. | 271.691 | per SQ.M. | 217.1181 | per SQ.M.
| FIXED METAL LOUVERS | 0.16026 | SQ.M.per hour | 0.32051 | SQ.M.per hour | 0.4 | SQ.M.per hour | 366.1667 | per SQ.M. | 183.0833 | per SQ.M. | 146.7014 | per SQ.M.
| FIXED GI SHEETS | 0.10799 | SQ.M.per hour | 0.21598 | SQ.M.per hour | 0.27027 | SQ.M.per hour | 543.3819 | per SQ.M. | 271.691 | per SQ.M. | 217.1181 | per SQ.M.
| FIXED GLASS | 0.15773 | SQ.M.per hour | 0.32051 | SQ.M.per hour | 0.4 | SQ.M.per hour | 372.0347 | per SQ.M. | 183.0833 | per SQ.M. | 146.7014 | per SQ.M.
| FIXED WOODEN | 0.14793 | SQ.M.per hour | 0.29586 | SQ.M.per hour | 0.37037 | SQ.M.per hour | 396.6806 | per SQ.M. | 198.3403 | per SQ.M. | 158.4375 | per SQ.M.
| ALUMINUM FRAME WINDOWS | 0.05 | EACHper hour | 0.1 | EACHper hour | 0.125 | EACHper hour | 1173.6111 | per EACH | 586.8056 | per EACH | 469.4444 | per EACH
| SLIDING GLASS DOOR | 0.041667 | EACHper hour | 0.083333 | EACHper hour | 0.10417 | EACHper hour | 1408.3333 | per EACH | 704.1667 | per EACH | 563.3333 | per EACH
| HOLLOW METAL DOOR | 0.05 | EACHper hour | 0.1 | EACHper hour | 0.125 | EACHper hour | 1173.6111 | per EACH | 586.8056 | per EACH | 469.4444 | per EACH
| ROLLING DOORS | 0.02 | EACHper hour | 0.04 | EACHper hour | 0.05 | EACHper hour | 2934.0278 | per EACH | 1467.0139 | per EACH | 1173.6111 | per EACH
| FIXED WINDOW | 1.5873 | S.F.per hour | 3.2258 | S.F.per hour | 4 | S.F.per hour | 36.9688 | per S.F. | 18.191 | per S.F. | 14.6701 | per S.F.
| DOOR LOCKSET | 0.3125 | SETper hour | 0.625 | SETper hour | 0.78125 | SETper hour | 187.7778 | per SET | 93.8889 | per SET | 75.1111 | per SET
| DOOR JAMB FABRICATION | 2.2727 | B.F.per hour | 4.5455 | B.F.per hour | 5.5556 | B.F.per hour | 25.8194 | per B.F. | 12.9097 | per B.F. | 10.5625 | per B.F.
| DOOR JAMB INSTALLATION | 1.5152 | B.F.per hour | 3.0303 | B.F.per hour | 3.8462 | B.F.per hour | 38.7292 | per B.F. | 19.3646 | per B.F. | 15.2569 | per B.F.
| CYCLONE WIRE INSTALLATION | 0.16026 | SQ.M.per hour | 0.32051 | SQ.M.per hour | 0.4 | SQ.M.per hour | 366.1667 | per SQ.M. | 183.0833 | per SQ.M. | 146.7014 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
F. | TRADE MASONRY WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GROUTING and TOL PLASTERING | 0.2994 | SQ.M.per hour | 0.5988 | SQ.M.per hour | 0.74627 | SQ.M.per hour | 195.9931 | per SQ.M. | 97.9965 | per SQ.M. | 78.6319 | per SQ.M.
| PEBBLE FINISHED | 0.34965 | SQ.M.per hour | 0.6993 | SQ.M.per hour | 0.74627 | SQ.M.per hour | 167.8264 | per SQ.M. | 83.9132 | per SQ.M. | 78.6319 | per SQ.M.
| MABLE INSTALLATION | 0.25 | SQ.M.per hour | 0.5 | SQ.M.per hour | 0.625 | SQ.M.per hour | 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M.
| 1/4" x 2' x 8" RED BRICKS | 0.1 | SQ.M.per hour | 0.2 | SQ.M.per hour | 0.25 | SQ.M.per hour | 586.8056 | per SQ.M. | 293.4028 | per SQ.M. | 234.7222 | per SQ.M.
| GLAZED TILES | 0.047483 | SQ.M.per hour | 0.094967 | SQ.M.per hour | 0.11876 | SQ.M.per hour | 1235.8125 | per SQ.M. | 617.9062 | per SQ.M. | 494.0903 | per SQ.M.
| UNGLAZED TILES | 0.11494 | SQ.M.per hour | 0.22989 | SQ.M.per hour | 0.28736 | SQ.M.per hour | 510.5208 | per SQ.M. | 255.2604 | per SQ.M. | 204.2083 | per SQ.M.
| GLAZED TILE WALL | 0.16667 | SQ.M.per hour | 0.33333 | SQ.M.per hour | 0.41667 | SQ.M.per hour | 352.0833 | per SQ.M. | 176.0417 | per SQ.M. | 140.8333 | per SQ.M.
| CONC. BLOCK INT. WALL | 0.11111 | SQ.M.per hour | 0.22222 | SQ.M.per hour | 0.27778 | SQ.M.per hour | 528.125 | per SQ.M. | 264.0625 | per SQ.M. | 211.25 | per SQ.M.
| CONC. BLOCK EXT. WALL | 0.125 | SQ.M.per hour | 0.25 | SQ.M.per hour | 0.3125 | SQ.M.per hour | 469.4444 | per SQ.M. | 234.7222 | per SQ.M. | 187.7778 | per SQ.M.
| BRICKWORK | 1 | SQ.M.per hour | 2 | SQ.M.per hour | 2.5 | SQ.M.per hour | 58.6806 | per SQ.M. | 29.3403 | per SQ.M. | 23.4722 | per SQ.M.
| PLASTER WALL AND CEILING | 0.16667 | SQ.M.per hour | 0.33333 | SQ.M.per hour | 0.29412 | SQ.M.per hour | 352.0833 | per SQ.M. | 176.0417 | per SQ.M. | 199.5139 | per SQ.M.
| HOLLOW TILE WALL | 0.25 | SQ.M.per hour | 0.5 | SQ.M.per hour | 0.625 | SQ.M.per hour | 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M.
| ACOUSTICAL TILE WALL | 0.41667 | SQ.M.per hour | 0.83333 | SQ.M.per hour | 1.0417 | SQ.M.per hour | 140.8333 | per SQ.M. | 70.4167 | per SQ.M. | 56.3333 | per SQ.M.
| VINYL FLOOR TILE | 0.27778 | SQ.M.per hour | 0.55556 | SQ.M.per hour | 0.69444 | SQ.M.per hour | 211.25 | per SQ.M. | 105.625 | per SQ.M. | 84.5 | per SQ.M.
| UNGLAZED OR MOSAIC FLOOR TILE | 0.058824 | SQ.M.per hour | 0.10526 | SQ.M.per hour | 0.14706 | SQ.M.per hour | 997.5694 | per SQ.M. | 557.4653 | per SQ.M. | 399.0278 | per SQ.M.
| LAYING OF CHB & ADOBE | 0.4386 | SQ.M.per hour | 0.87719 | SQ.M.per hour | 1.0989 | SQ.M.per hour | 133.7917 | per SQ.M. | 66.8958 | per SQ.M. | 53.3993 | per SQ.M.
| CEMENT FINISH | 0.6993 | SQ.M.per hour | 1.3889 | SQ.M.per hour | 1.7544 | SQ.M.per hour | 83.9132 | per SQ.M. | 42.25 | per SQ.M. | 33.4479 | per SQ.M.
| CONC. HOLLOW BLOCK LAYING: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 6" CHB | 0.3125 | SQ.M.per hour | 0.625 | SQ.M.per hour | 0.78125 | SQ.M.per hour | 187.7778 | per SQ.M. | 93.8889 | per SQ.M. | 75.1111 | per SQ.M.
| 4" CHB | 0.37594 | SQ.M.per hour | 0.75188 | SQ.M.per hour | 0.9434 | SQ.M.per hour | 156.0903 | per SQ.M. | 78.0451 | per SQ.M. | 62.2014 | per SQ.M.
| 8" CHB | 0.25 | SQ.M.per hour | 0.5 | SQ.M.per hour | 0.625 | SQ.M.per hour | 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M.
| VIT. TILES FLOOR | 0.093809 | SQ.M.per hour | 0.18762 | SQ.M.per hour | 0.23474 | SQ.M.per hour | 625.5347 | per SQ.M. | 312.7674 | per SQ.M. | 249.9792 | per SQ.M.
| VIT. TILES WALL | 0.083752 | SQ.M.per hour | 0.1675 | SQ.M.per hour | 0.20921 | SQ.M.per hour | 700.6458 | per SQ.M. | 350.3229 | per SQ.M. | 280.4931 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
G. | TINSMITHING WORK | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CORR GI SHEETS: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LIFTING | 0.46296 | SQ.M.per hour | 0.92593 | SQ.M.per hour | 1.1628 | SQ.M.per hour | 126.75 | per SQ.M. | 63.375 | per SQ.M. | 50.4653 | per SQ.M.
| INSTALLATION | 0.1634 | SQ.M.per hour | 0.3268 | SQ.M.per hour | 0.40816 | SQ.M.per hour | 359.125 | per SQ.M. | 179.5625 | per SQ.M. | 143.7674 | per SQ.M.
| INSTALLATION OF ASBESTOS ROOFING | 0.5 | SHT.per hour | 1 | SHT.per hour | 1.25 | SHT.per hour | 117.3611 | per SHT. | 58.6806 | per SHT. | 46.9444 | per SHT.
| INSTALLATION OF ALUMINUM GI SHEET | 0.625 | SHT.per hour | 0.10204 | SHT.per hour | 1.5625 | SHT.per hour | 93.8889 | per SHT. | 575.0694 | per SHT. | 37.5556 | per SHT.
| COPPER CLADDING ROOF DECK | 0.9901 | L.M.per hour | 1.9608 | L.M.per hour | 2.5 | L.M.per hour | 59.2674 | per L.M. | 29.9271 | per L.M. | 23.4722 | per L.M.
| FAB, GI GUTTER | 0.14409 | SHT.per hour | 0.28818 | SHT.per hour | 0.35971 | SHT.per hour | 407.2431 | per SHT. | 203.6215 | per SHT. | 163.1319 | per SHT.
| GI SHEET ROOFING | 0.60976 | SHT.per hour | 1.2195 | SHT.per hour | 1.5152 | SHT.per hour | 96.2361 | per SHT. | 48.1181 | per SHT. | 38.7292 | per SHT.
| FAB OF GI GUTTER | 0.95238 | L.M.per hour | 1.8868 | L.M.per hour | 2.381 | L.M.per hour | 61.6146 | per L.M. | 31.1007 | per L.M. | 24.6458 | per L.M.
| FAB. GI DOWNSPOUT | 0.51546 | L.M.per hour | 1.0309 | L.M.per hour | 0.5618 | L.M.per hour | 113.8403 | per L.M. | 56.9201 | per L.M. | 104.4514 | per L.M.
| GUTTER CUT & SHAPE | 3.125 | L.M.per hour | 6.25 | L.M.per hour | 7.6923 | L.M.per hour | 18.7778 | per L.M. | 9.3889 | per L.M. | 7.6285 | per L.M.
| INST. OF GUTTER | 0.5618 | L.M.per hour | 0.11111 | L.M.per hour | 1.4085 | L.M.per hour | 104.4514 | per L.M. | 528.125 | per L.M. | 41.6632 | per L.M.
| DOWNSPOUT CUT AND SHAPE | 1.6949 | L.M.per hour | 3.3333 | L.M.per hour | 4.1667 | L.M.per hour | 34.6215 | per L.M. | 17.6042 | per L.M. | 14.0833 | per L.M.
| DOWNSPOUT INSTALLATION | 3.7037 | L.M.per hour | 7.6923 | L.M.per hour | 9.0909 | L.M.per hour | 15.8438 | per L.M. | 7.6285 | per L.M. | 6.4549 | per L.M.
| CORR. GI ROOFING | 0.27778 | SQ.M.per hour | 0.55556 | SQ.M.per hour | 0.69444 | SQ.M.per hour | 211.25 | per SQ.M. | 105.625 | per SQ.M. | 84.5 | per SQ.M.
| CORR ALUMINUM ROOFING | 0.27778 | SQ.M.per hour | 0.55556 | SQ.M.per hour | 0.69444 | SQ.M.per hour | 211.25 | per SQ.M. | 105.625 | per SQ.M. | 84.5 | per SQ.M.
| BUILT UP ROOFING 4 PLY | 0.058824 | SQ.M.per hour | 0.11765 | SQ.M.per hour | 0.14706 | SQ.M.per hour | 997.5694 | per SQ.M. | 498.7847 | per SQ.M. | 399.0278 | per SQ.M.
| PROTECTED METAL | 0.25 | SQ.M.per hour | 0.5 | SQ.M.per hour | 0.625 | SQ.M.per hour | 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M.
| CORR. ASBESTOS INST., LIFTING & HAULING | 0.29412 | SQ.M.per hour | 0.58824 | SQ.M.per hour | 0.73529 | SQ.M.per hour | 199.5139 | per SQ.M. | 99.7569 | per SQ.M. | 79.8056 | per SQ.M.
| LEADERS & GUTTERS | 0.83333 | SQ.M.per hour | 1.6667 | SQ.M.per hour | 2.0833 | SQ.M.per hour | 70.4167 | per SQ.M. | 35.2083 | per SQ.M. | 28.1667 | per SQ.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
H | CONCRETE AND REBAR WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PLACING CONCRETE: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SLAB ON FILL | 0.1 | CU.M.per hour | 0.2 | CU.M.per hour | 0.25 | CU.M.per hour | 586.8056 | per CU.M. | 293.4028 | per CU.M. | 234.7222 | per CU.M.
| SLIP FORM | 0.02 | CU.M.per hour | 0.04 | CU.M.per hour | 0.05 | CU.M.per hour | 2934.0278 | per CU.M. | 1467.0139 | per CU.M. | 1173.6111 | per CU.M.
| FLR FINISH UNHARDENED | 0.5 | SQ.M.per hour | 1 | SQ.M.per hour | 1.25 | SQ.M.per hour | 117.3611 | per SQ.M. | 58.6806 | per SQ.M. | 46.9444 | per SQ.M.
| CONC. FINISH HARDENED | 0.34965 | SQ.M.per hour | 0.6993 | SQ.M.per hour | 0.87719 | SQ.M.per hour | 167.8264 | per SQ.M. | 83.9132 | per SQ.M. | 66.8958 | per SQ.M.
| REBAR WORKS: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GROUND FLR. INSTALLATION | 7.1429 | KGSper hour | 14.2857 | KGSper hour | 16.6667 | KGSper hour | 8.2153 | per KGS | 4.1076 | per KGS | 3.5208 | per KGS
| UPPER FLR. INSTALLATION | 6.25 | KGSper hour | 12.5 | KGSper hour | 16.6667 | KGSper hour | 9.3889 | per KGS | 4.6944 | per KGS | 3.5208 | per KGS
| FABRICATION | 5 | KGSper hour | 10 | KGSper hour | 12.5 | KGSper hour | 11.7361 | per KGS | 5.8681 | per KGS | 4.6944 | per KGS
| MIXING MANUAL | 0.03125 | CU.M.per hour | 0.0625 | CU.M.per hour | 0.078125 | CU.M.per hour | 1877.7778 | per CU.M. | 938.8889 | per CU.M. | 751.1111 | per CU.M.
| MIXING MACHINE | 0.27778 | CU.M.per hour | 0.55556 | CU.M.per hour | 0.69444 | CU.M.per hour | 211.25 | per CU.M. | 105.625 | per CU.M. | 84.5 | per CU.M.
| MORE THAN 1.80 CU.M. POUR: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CHUTE FROM TRUCK | 0.071429 | CU.M.per hour | 0.14286 | CU.M.per hour | 0.17857 | CU.M.per hour | 821.5278 | per CU.M. | 410.7639 | per CU.M. | 328.6111 | per CU.M.
| CRANE AND BUCKET | 0.035714 | CU.M.per hour | 0.071429 | CU.M.per hour | 0.089286 | CU.M.per hour | 1643.0556 | per CU.M. | 821.5278 | per CU.M. | 657.2222 | per CU.M.
| WHEELING | 0.018519 | CU.M.per hour | 0.037037 | CU.M.per hour | 0.046296 | CU.M.per hour | 3168.75 | per CU.M. | 1584.375 | per CU.M. | 1267.5 | per CU.M.
| FINISHING | 0.17857 | SQ.M.per hour | 0.35714 | SQ.M.per hour | 0.44643 | SQ.M.per hour | 328.6111 | per SQ.M. | 164.3056 | per SQ.M. | 131.4444 | per SQ.M.
| CONCRETE POUR ON ELEVATED AND SHORED | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SLAB FORMING CHUTE & BUCKET | 0.02381 | CU.M.per hour | 0.047619 | CU.M.per hour | 0.059524 | CU.M.per hour | 2464.5833 | per CU.M. | 1232.2917 | per CU.M. | 985.8333 | per CU.M.
| PLACEMENT OF REBARS ON FOOTING | 0.9434 | KGSper hour | 1.8868 | KGSper hour | 2.381 | KGSper hour | 62.2014 | per KGS | 31.1007 | per KGS | 24.6458 | per KGS
| FIELD FABRICATION OF REBARS | 1.5152 | KGSper hour | 3.0303 | KGSper hour | 3.8462 | KGSper hour | 38.7292 | per KGS | 19.3646 | per KGS | 15.2569 | per KGS
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
I. | EARTH WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MACHINE EXCAVATION: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SAND | 0.83333 | CU.M.per hour | 1.6667 | CU.M.per hour | 2.0833 | CU.M.per hour | 70.4167 | per CU.M. | 35.2083 | per CU.M. | 28.1667 | per CU.M.
| SAND AND MARL | 0.625 | CU.M.per hour | 1.25 | CU.M.per hour | 1.5625 | CU.M.per hour | 93.8889 | per CU.M. | 46.9444 | per CU.M. | 37.5556 | per CU.M.
| MARL | 0.45455 | CU.M.per hour | 0.90909 | CU.M.per hour | 1.1364 | CU.M.per hour | 129.0972 | per CU.M. | 64.5486 | per CU.M. | 51.6389 | per CU.M.
| GRANULAR BACKFILL | 0.41667 | CU.M.per hour | 0.83333 | CU.M.per hour | 1.0417 | CU.M.per hour | 140.8333 | per CU.M. | 70.4167 | per CU.M. | 56.3333 | per CU.M.
| GRANULAR SOIL BACKFILL | 0.33333 | CU.M.per hour | 0.66667 | CU.M.per hour | 0.83333 | CU.M.per hour | 176.0417 | per CU.M. | 88.0208 | per CU.M. | 70.4167 | per CU.M.
| MANUAL FOUNDATION EXCAVATION & BACKFILL: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SAND | 0.125 | CU.M.per hour | 0.25 | CU.M.per hour | 0.3125 | CU.M.per hour | 469.4444 | per CU.M. | 234.7222 | per CU.M. | 187.7778 | per CU.M.
| EXCAVATION OF SAND &MARL | 0.076923 | CU.M.per hour | 0.15385 | CU.M.per hour | 0.19231 | CU.M.per hour | 762.8472 | per CU.M. | 381.4236 | per CU.M. | 305.1389 | per CU.M.
| EXCAVATION OF MARL | 0.047619 | CU.M.per hour | 0.095238 | CU.M.per hour | 0.11905 | CU.M.per hour | 1232.2917 | per CU.M. | 616.1458 | per CU.M. | 492.9167 | per CU.M.
| BACKFILL OF SAND | 0.090909 | CU.M.per hour | 0.18182 | CU.M.per hour | 0.22727 | CU.M.per hour | 645.4861 | per CU.M. | 322.7431 | per CU.M. | 258.1944 | per CU.M.
| BACKFILL OF SAND &MARL | 0.0625 | CU.M.per hour | 0.125 | CU.M.per hour | 0.15625 | CU.M.per hour | 938.8889 | per CU.M. | 469.4444 | per CU.M. | 375.5556 | per CU.M.
| BACKFILL OF MARL | 0.041667 | CU.M.per hour | 0.083333 | CU.M.per hour | 0.10417 | CU.M.per hour | 1408.3333 | per CU.M. | 704.1667 | per CU.M. | 563.3333 | per CU.M.
| FLOOR SLAB & GRADE: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GRADING MANUAL | 0.38462 | SQ.M.per hour | 0.76923 | SQ.M.per hour | 0.96154 | SQ.M.per hour | 152.5694 | per SQ.M. | 76.2847 | per SQ.M. | 61.0278 | per SQ.M.
| EXCAVATION AND BACKFILL | 0.027778 | CU.M.per hour | 0.055556 | CU.M.per hour | 0.069444 | CU.M.per hour | 2112.5 | per CU.M. | 1056.25 | per CU.M. | 845 | per CU.M.
| FINE GRADING & FINISHING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GRADING MANUAL | 1.1111 | SQ.M.per hour | 2.2222 | SQ.M.per hour | 2.7778 | SQ.M.per hour | 52.8125 | per SQ.M. | 26.4062 | per SQ.M. | 21.125 | per SQ.M.
| FINISHING SOIL SURFACE | 0.90909 | SQ.M.per hour | 1.8182 | SQ.M.per hour | 2.2727 | SQ.M.per hour | 64.5486 | per SQ.M. | 32.2743 | per SQ.M. | 25.8194 | per SQ.M.
| DIKES | 0.41667 | CU.M.per hour | 0.83333 | CU.M.per hour | 1.0417 | CU.M.per hour | 140.8333 | per CU.M. | 70.4167 | per CU.M. | 56.3333 | per CU.M.
J | ROAD WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| BASE COURSE | 4.1667 | SQ.M.per hour | 8.3333 | SQ.M.per hour | 10 | SQ.M.per hour | 14.0833 | per SQ.M. | 7.0417 | per SQ.M. | 5.8681 | per SQ.M.
| CURBS & GUTTER | 0.27778 | CU.M.per hour | 0.55556 | CU.M.per hour | 0.69444 | CU.M.per hour | 211.25 | per CU.M. | 105.625 | per CU.M. | 84.5 | per CU.M.
| 4" THK ROAD | 0.38462 | SQ.M.per hour | 0.76923 | SQ.M.per hour | 0.96154 | SQ.M.per hour | 152.5694 | per SQ.M. | 76.2847 | per SQ.M. | 61.0278 | per SQ.M.
| 6" THK ROAD | 0.35714 | SQ.M.per hour | 0.71429 | SQ.M.per hour | 0.89286 | SQ.M.per hour | 164.3056 | per SQ.M. | 82.1528 | per SQ.M. | 65.7222 | per SQ.M.
| 8" THK ROAD | 0.33333 | SQ.M.per hour | 0.66667 | SQ.M.per hour | 0.83333 | SQ.M.per hour | 176.0417 | per SQ.M. | 88.0208 | per SQ.M. | 70.4167 | per SQ.M.
| TROWEL FINISH | 1.5625 | SQ.M.per hour | 3.125 | SQ.M.per hour | 3.8462 | SQ.M.per hour | 37.5556 | per SQ.M. | 18.7778 | per SQ.M. | 15.2569 | per SQ.M.
| SPECIAL TOPPING | 0.41667 | SQ.M.per hour | 0.83333 | SQ.M.per hour | 1.0417 | SQ.M.per hour | 140.8333 | per SQ.M. | 70.4167 | per SQ.M. | 56.3333 | per SQ.M.
| 4" STONE OR SHELL ROAD | 1.5625 | SQ.M.per hour | 3.125 | SQ.M.per hour | 3.8462 | SQ.M.per hour | 37.5556 | per SQ.M. | 18.7778 | per SQ.M. | 15.2569 | per SQ.M.
| 6" STONE OR SHELL ROAD | 1.1905 | SQ.M.per hour | 2.381 | SQ.M.per hour | 2.9412 | SQ.M.per hour | 49.2917 | per SQ.M. | 24.6458 | per SQ.M. | 19.9514 | per SQ.M.
| 8" STONE OR SHELL ROAD | 0.96154 | SQ.M.per hour | 1.9231 | SQ.M.per hour | 2.381 | SQ.M.per hour | 61.0278 | per SQ.M. | 30.5139 | per SQ.M. | 24.6458 | per SQ.M.
| ACID PROOFING | 0.83333 | CU.M.per hour | 1.6667 | CU.M.per hour | 2.0833 | CU.M.per hour | 70.4167 | per CU.M. | 35.2083 | per CU.M. | 28.1667 | per CU.M.
| ASPHALT PAVING: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FINE GRADING & FINISHING | 1.1905 | SQ.M.per hour | 2.381 | SQ.M.per hour | 2.9412 | SQ.M.per hour | 49.2917 | per SQ.M. | 24.6458 | per SQ.M. | 19.9514 | per SQ.M.
| PLACE BASE COURSE | 2.5 | SQ.M.per hour | 5 | SQ.M.per hour | 6.25 | SQ.M.per hour | 23.4722 | per SQ.M. | 11.7361 | per SQ.M. | 9.3889 | per SQ.M.
| ASPHALT | 2.5 | SQ.M.per hour | 5 | SQ.M.per hour | 6.25 | SQ.M.per hour | 23.4722 | per SQ.M. | 11.7361 | per SQ.M. | 9.3889 | per SQ.M.
| ACID BLOCK OR PAVING BLOCK: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIND GRADING | 1.1905 | SQ.M.per hour | 2.381 | SQ.M.per hour | 2.9412 | SQ.M.per hour | 49.2917 | per SQ.M. | 24.6458 | per SQ.M. | 19.9514 | per SQ.M.
| INSTALL BRICK | 0.11905 | SQ.M.per hour | 0.2381 | SQ.M.per hour | 0.29762 | SQ.M.per hour | 492.9167 | per SQ.M. | 246.4583 | per SQ.M. | 197.1667 | per SQ.M.
| CRUSH STONE OR SHELL SURFACING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FINE GRADING | 1.5625 | SQ.M.per hour | 3.125 | SQ.M.per hour | 3.8462 | SQ.M.per hour | 37.5556 | per SQ.M. | 18.7778 | per SQ.M. | 15.2569 | per SQ.M.
| PLACE SPREAD AND COMPACT STONE TO 4" | 1.1905 | SQ.M.per hour | 2.381 | SQ.M.per hour | 2.9412 | SQ.M.per hour | 49.2917 | per SQ.M. | 24.6458 | per SQ.M. | 19.9514 | per SQ.M.
| OVER 9" THK | 0.96154 | SQ.M.per hour | 1.9231 | SQ.M.per hour | 2.381 | SQ.M.per hour | 61.0278 | per SQ.M. | 30.5139 | per SQ.M. | 24.6458 | per SQ.M.
| TANK CUSHION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SAND CUSHION | 0.71429 | CU.M.per hour | 1.4286 | CU.M.per hour | 1.7857 | CU.M.per hour | 82.1528 | per CU.M. | 41.0764 | per CU.M. | 32.8611 | per CU.M.
| APHALT RETAINER RING | 2.5 | SQ.M.per hour | 5 | SQ.M.per hour | 6.25 | SQ.M.per hour | 23.4722 | per SQ.M. | 11.7361 | per SQ.M. | 9.3889 | per SQ.M.
| NON GRANULAR BACKFILL | 0.25 | CU.M.per hour | 0.5 | CU.M.per hour | 0.625 | CU.M.per hour | 234.7222 | per CU.M. | 117.3611 | per CU.M. | 93.8889 | per CU.M.
| EXCAVATION MANUAL: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMMON EARTH | 0.0625 | CU.M.per hour | 0.125 | CU.M.per hour | 0.15625 | CU.M.per hour | 938.8889 | per CU.M. | 469.4444 | per CU.M. | 375.5556 | per CU.M.
| LOAN OF SAND | 0.38168 | CU.M.per hour | 0.76336 | CU.M.per hour | 0.95238 | CU.M.per hour | 153.7431 | per CU.M. | 76.8715 | per CU.M. | 61.6146 | per CU.M.
| CLAY OR HEAVY SOIL ROCK | 0.30488 | CU.M.per hour | 0.60976 | CU.M.per hour | 0.76336 | CU.M.per hour | 192.4722 | per CU.M. | 96.2361 | per CU.M. | 76.8715 | per CU.M.
| ROCK | 0.19011 | CU.M.per hour | 0.38023 | CU.M.per hour | 0.47619 | CU.M.per hour | 308.6597 | per CU.M. | 154.3299 | per CU.M. | 123.2292 | per CU.M.
| MECHANICAL EXCAVATION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMMON EARTH | 0.074963 | CU.M.per hour | 0.14993 | CU.M.per hour | 0.18727 | CU.M.per hour | 782.7986 | per CU.M. | 391.3993 | per CU.M. | 313.3542 | per CU.M.
| ROCK W/ JACKHAMMER | 0.029994 | CU.M.per hour | 0.059988 | CU.M.per hour | 0.074963 | CU.M.per hour | 1956.4097 | per CU.M. | 978.2049 | per CU.M. | 782.7986 | per CU.M.
| BACKFILLING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| COMMON MANUAL | 0.60976 | CU.M.per hour | 1.2195 | CU.M.per hour | 1.5152 | CU.M.per hour | 96.2361 | per CU.M. | 48.1181 | per CU.M. | 38.7292 | per CU.M.
| GRAVEL FILL MANUAL | 0.1 | CU.M.per hour | 0.2 | CU.M.per hour | 0.25 | CU.M.per hour | 586.8056 | per CU.M. | 293.4028 | per CU.M. | 234.7222 | per CU.M.
| TRENCHING AND BACKFILLING OF UNDERGROUND | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| PIPING USING EXCAVATION MATERIALS MANUAL | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FROM 0 TO 2 MTRS. DEPTH | 0.4 | L.M.per hour | 0.8 | L.M.per hour | 1 | L.M.per hour | 146.7014 | per L.M. | 73.3507 | per L.M. | 58.6806 | per L.M.
| 2 TO 3 | 0.2994 | L.M.per hour | 0.5988 | L.M.per hour | 0.42735 | L.M.per hour | 195.9931 | per L.M. | 97.9965 | per L.M. | 137.3125 | per L.M.
| 3 TO 4 | 0.2 | L.M.per hour | 0.4 | L.M.per hour | 0.5 | L.M.per hour | 293.4028 | per L.M. | 146.7014 | per L.M. | 117.3611 | per L.M.
| 4 TO 5 | 0.15015 | L.M.per hour | 0.3003 | L.M.per hour | 0.37594 | L.M.per hour | 390.8125 | per L.M. | 195.4062 | per L.M. | 156.0903 | per L.M.
| PLACING BINDER GRAVEL | 4.7619 | CU.M.per hour | 9.0909 | CU.M.per hour | 12.5 | CU.M.per hour | 12.3229 | per CU.M. | 6.4549 | per CU.M. | 4.6944 | per CU.M.
| ESCOMBRO BACKFILLING | 2.381 | CU.M.per hour | 4.7619 | CU.M.per hour | 5.8824 | CU.M.per hour | 24.6458 | per CU.M. | 12.3229 | per CU.M. | 9.9757 | per CU.M.
| SPREADING, TAMPING AND GRADING | 1.0417 | SQ.M.per hour | 2.0833 | SQ.M.per hour | 2.6316 | SQ.M.per hour | 56.3333 | per SQ.M. | 28.1667 | per SQ.M. | 22.2986 | per SQ.M.
| MECHANICAL COMPACTION, PLATE COMPACTION | 9.0909 | CU.M.per hour | 16.6667 | CU.M.per hour | 25 | CU.M.per hour | 6.4549 | per CU.M. | 3.5208 | per CU.M. | 2.3472 | per CU.M.
| MANUAL CLEARING AND GRUBBING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| CLEARING UNDERGROWTH AND TREES 12" | 10 | SQ.M.per hour | 20 | SQ.M.per hour | 25 | SQ.M.per hour | 5.8681 | per SQ.M. | 2.934 | per SQ.M. | 2.3472 | per SQ.M.
| CLEARING UNDERGROWTH AND SHRUBS | 16.6667 | SQ.M.per hour | 33.3333 | SQ.M.per hour | 50 | SQ.M.per hour | 3.5208 | per SQ.M. | 1.7604 | per SQ.M. | 1.1736 | per SQ.M.
| DISPOSAL OF SOIL | 0.29586 | CU.M.per hour | 0.59172 | CU.M.per hour | 0.74074 | CU.M.per hour | 198.3403 | per CU.M. | 99.1701 | per CU.M. | 79.2188 | per CU.M.
| MAULING OF SOIL | 0.5 | CU.M.per hour | 1 | CU.M.per hour | 1.25 | CU.M.per hour | 117.3611 | per CU.M. | 58.6806 | per CU.M. | 46.9444 | per CU.M.
| GRAVEL FILL | 0.24155 | CU.M.per hour | 0.48309 | CU.M.per hour | 0.60241 | CU.M.per hour | 242.9375 | per CU.M. | 121.4688 | per CU.M. | 97.4097 | per CU.M.
| EXCAVATION CRANE AND CLAMPSHELL | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
. | WITH 8-MEN AND 2 CARPENTERS | 0.46729 | CU.M.per hour | 0.93458 | CU.M.per hour | 1.1628 | CU.M.per hour | 125.5764 | per CU.M. | 62.7882 | per CU.M. | 50.4653 | per CU.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
K. | TRADE: UNDERGROUND PIPING AND PLUMBING WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
1 | LAYING ASBESTOS PIPES: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1//2Ø | 0.75758 | L.M.per hour | 1.5152 | L.M.per hour | 1.8868 | L.M.per hour | 77.4583 | per L.M. | 38.7292 | per L.M. | 31.1007 | per L.M.
| 3/4" Ø | 0.75758 | L.M.per hour | 1.5152 | L.M.per hour | 1.8868 | L.M.per hour | 77.4583 | per L.M. | 38.7292 | per L.M. | 31.1007 | per L.M.
| 1 1/4" | 0.67568 | L.M.per hour | 1.3514 | L.M.per hour | 1.6949 | L.M.per hour | 86.8472 | per L.M. | 43.4236 | per L.M. | 34.6215 | per L.M.
| 1 1/2 TO 2" Ø | 0.60976 | L.M.per hour | 1.2195 | L.M.per hour | 1.5152 | L.M.per hour | 96.2361 | per L.M. | 48.1181 | per L.M. | 38.7292 | per L.M.
| 2 1/2" Ø | 0.50761 | L.M.per hour | 1.0204 | L.M.per hour | 1.4286 | L.M.per hour | 115.6007 | per L.M. | 57.5069 | per L.M. | 41.0764 | per L.M.
| 3" Ø | 0.46296 | L.M.per hour | 0.92593 | L.M.per hour | 1.1628 | L.M.per hour | 126.75 | per L.M. | 63.375 | per L.M. | 50.4653 | per L.M.
| 3 1/2" Ø | 0.43478 | L.M.per hour | 0.86957 | L.M.per hour | 1.087 | L.M.per hour | 134.9653 | per L.M. | 67.4826 | per L.M. | 53.9861 | per L.M.
| 4" Ø | 0.37879 | L.M.per hour | 0.75758 | L.M.per hour | 0.9434 | L.M.per hour | 154.9167 | per L.M. | 77.4583 | per L.M. | 62.2014 | per L.M.
2 | CAST IRON PIPE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2" Ø | 0.22831 | L.M.per hour | 0.45662 | L.M.per hour | 0.57143 | L.M.per hour | 257.0208 | per L.M. | 128.5104 | per L.M. | 102.691 | per L.M.
| 4" Ø | 0.15198 | L.M.per hour | 0.30395 | L.M.per hour | 0.38023 | L.M.per hour | 386.1181 | per L.M. | 193.059 | per L.M. | 154.3299 | per L.M.
| 6" Ø | 0.10163 | L.M.per hour | 0.20325 | L.M.per hour | 0.25381 | L.M.per hour | 577.4167 | per L.M. | 288.7083 | per L.M. | 231.2014 | per L.M.
| 8" Ø | 0.076104 | L.M.per hour | 0.15221 | L.M.per hour | 0.19011 | L.M.per hour | 771.0625 | per L.M. | 385.5312 | per L.M. | 308.6597 | per L.M.
| 10" Ø | 0.050761 | L.M.per hour | 0.10152 | L.M.per hour | 0.12531 | L.M.per hour | 1156.0069 | per L.M. | 578.0035 | per L.M. | 468.2708 | per L.M.
| 12" Ø | 0.048497 | L.M.per hour | 0.096993 | L.M.per hour | 0.12121 | L.M.per hour | 1209.9931 | per L.M. | 604.9965 | per L.M. | 484.1146 | per L.M.
| 14" Ø | 0.041494 | L.M.per hour | 0.082988 | L.M.per hour | 0.10373 | L.M.per hour | 1414.2014 | per L.M. | 707.1007 | per L.M. | 565.6806 | per L.M.
| 16" Ø | 0.036523 | L.M.per hour | 0.073046 | L.M.per hour | 0.091324 | L.M.per hour | 1606.6736 | per L.M. | 803.3368 | per L.M. | 642.5521 | per L.M.
| 18" Ø | 0.032595 | L.M.per hour | 0.065189 | L.M.per hour | 0.0815 | L.M.per hour | 1800.3194 | per L.M. | 900.1597 | per L.M. | 720.0104 | per L.M.
| 20" Ø | 0.030432 | L.M.per hour | 0.060864 | L.M.per hour | 0.076104 | L.M.per hour | 1928.2431 | per L.M. | 964.1215 | per L.M. | 771.0625 | per L.M.
| 24" Ø | 0.02767 | L.M.per hour | 0.05534 | L.M.per hour | 0.069156 | L.M.per hour | 2120.7153 | per L.M. | 1060.3576 | per L.M. | 848.5208 | per L.M.
| 30" Ø | 0.024343 | L.M.per hour | 0.048685 | L.M.per hour | 0.060864 | L.M.per hour | 2410.5972 | per L.M. | 1205.2986 | per L.M. | 964.1215 | per L.M.
3 | LAYING PVC PIPE | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 1/2 TO 3/4" Ø | 2.6316 | L.M.per hour | 5.2632 | L.M.per hour | 6.6667 | L.M.per hour | 22.2986 | per L.M. | 11.1493 | per L.M. | 8.8021 | per L.M.
| 1 TO 1 1/4" Ø | 0.67568 | L.M.per hour | 1.3514 | L.M.per hour | 1.6949 | L.M.per hour | 86.8472 | per L.M. | 43.4236 | per L.M. | 34.6215 | per L.M.
| 1 1/2 TO 2" Ø | 0.60976 | L.M.per hour | 1.2195 | L.M.per hour | 1.5152 | L.M.per hour | 96.2361 | per L.M. | 48.1181 | per L.M. | 38.7292 | per L.M.
| 2 1/2" Ø | 0.5102 | L.M.per hour | 1.0204 | L.M.per hour | 1.2821 | L.M.per hour | 115.0139 | per L.M. | 57.5069 | per L.M. | 45.7708 | per L.M.
| 3" Ø | 0.46296 | L.M.per hour | 0.92593 | L.M.per hour | 1.1628 | L.M.per hour | 126.75 | per L.M. | 63.375 | per L.M. | 50.4653 | per L.M.
| 4" Ø | 0.38168 | L.M.per hour | 0.76336 | L.M.per hour | 0.95238 | L.M.per hour | 153.7431 | per L.M. | 76.8715 | per L.M. | 61.6146 | per L.M.
| 5" Ø | 0.30488 | L.M.per hour | 0.60976 | L.M.per hour | 0.76336 | L.M.per hour | 192.4722 | per L.M. | 96.2361 | per L.M. | 76.8715 | per L.M.
| 6" Ø | 0.20325 | L.M.per hour | 0.4065 | L.M.per hour | 0.50761 | L.M.per hour | 288.7083 | per L.M. | 144.3542 | per L.M. | 115.6007 | per L.M.
4 | LAYING RCP 8 MEN (1 TEAM) | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 24"Ø | 0.11111 | L.M.per hour | 0.25 | L.M.per hour | 0.3125 | L.M.per hour | 528.125 | per L.M. | 234.7222 | per L.M. | 187.7778 | per L.M.
| 36"Ø | 0.078125 | L.M.per hour | 0.15625 | L.M.per hour | 0.19531 | L.M.per hour | 751.1111 | per L.M. | 375.5556 | per L.M. | 300.4444 | per L.M.
| 48"Ø | 0.04686 | L.M.per hour | 0.093721 | L.M.per hour | 0.1171 | L.M.per hour | 1252.2431 | per L.M. | 626.1215 | per L.M. | 501.1319 | per L.M.
| 6-18"Ø | 0.37594 | L.M.per hour | 0.75188 | L.M.per hour | 0.9434 | L.M.per hour | 156.0903 | per L.M. | 78.0451 | per L.M. | 62.2014 | per L.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| LAVATORY | 0.0625 | EACHper hour | 0.125 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 469.4444 | per EACH | 375.5556 | per EACH
| WATER CLOSET | 0.041667 | EACHper hour | 0.083333 | EACHper hour | 0.10417 | EACHper hour | 1408.3333 | per EACH | 704.1667 | per EACH | 563.3333 | per EACH
| URINAL UTILITY STALL | 0.020833 | EACHper hour | 0.041667 | EACHper hour | 0.052083 | EACHper hour | 2816.6667 | per EACH | 1408.3333 | per EACH | 1126.6667 | per EACH
| URINAL PEDESTRAL TYPE | 0.03125 | EACHper hour | 0.0625 | EACHper hour | 0.078125 | EACHper hour | 1877.7778 | per EACH | 938.8889 | per EACH | 751.1111 | per EACH
| SHOWER AND INSTALL | 0.05 | EACHper hour | 0.1 | EACHper hour | 0.125 | EACHper hour | 1173.6111 | per EACH | 586.8056 | per EACH | 469.4444 | per EACH
| 5 MAN GROUP SHOWER | 0.013889 | EACHper hour | 0.027778 | EACHper hour | 0.034722 | EACHper hour | 4225 | per EACH | 2112.5 | per EACH | 1690 | per EACH
| BAH TUBS | 0.020833 | EACHper hour | 0.041667 | EACHper hour | 0.052083 | EACHper hour | 2816.6667 | per EACH | 1408.3333 | per EACH | 1126.6667 | per EACH
| SLOPE SINK | 0.035714 | EACHper hour | 0.071429 | EACHper hour | 0.089286 | EACHper hour | 1643.0556 | per EACH | 821.5278 | per EACH | 657.2222 | per EACH
| HOT WATER HEATER | 0.035714 | EACHper hour | 0.071429 | EACHper hour | 0.089286 | EACHper hour | 1643.0556 | per EACH | 821.5278 | per EACH | 657.2222 | per EACH
| 16 PERSON WASH SINK | 0.019231 | EACHper hour | 0.038462 | EACHper hour | 0.048077 | EACHper hour | 3051.3889 | per EACH | 1525.6944 | per EACH | 1220.5556 | per EACH
| DRINKING FOUNTAIN | 0.038462 | EACHper hour | 0.076923 | EACHper hour | 0.096154 | EACHper hour | 1525.6944 | per EACH | 762.8472 | per EACH | 610.2778 | per EACH
| EYE WASH | 0.0625 | EACHper hour | 0.11111 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 528.125 | per EACH | 375.5556 | per EACH
| MISC. FIXTURES | 0.25 | EACHper hour | 0.5 | EACHper hour | 0.625 | EACHper hour | 234.7222 | per EACH | 117.3611 | per EACH | 93.8889 | per EACH
| PARTITIONS | 0.0625 | EACHper hour | 0.125 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 469.4444 | per EACH | 375.5556 | per EACH
| LAYING OF 24"Ø RCP | 0.125 | PIPEper hour | 0.25 | PIPEper hour | 0.3125 | PIPEper hour | 469.4444 | per PIPE | 234.7222 | per PIPE | 187.7778 | per PIPE
| LAYING OF 36"Ø RCP | 0.078125 | PIPEper hour | 0.15625 | PIPEper hour | 0.19531 | PIPEper hour | 751.1111 | per PIPE | 375.5556 | per PIPE | 300.4444 | per PIPE
| LAYING OF 48"Ø RCP | 0.046904 | PIPEper hour | 0.093809 | PIPEper hour | 0.11723 | PIPEper hour | 1251.0694 | per PIPE | 625.5347 | per PIPE | 500.5451 | per PIPE
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
L. | TRADE INSULATION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EQUIPMENT INSTALLATION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| VESSEL, EXCHANGE & TANKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD FABRICATION INSULATION | 0.2 | S.M.per hour | 0.4 | S.M.per hour | 0.5 | S.M.per hour | 293.4028 | per S.M. | 146.7014 | per S.M. | 117.3611 | per S.M.
| FIELD FABRICATION SHEET METAL COVER | 0.041667 | S.M.per hour | 0.083333 | S.M.per hour | 0.10417 | S.M.per hour | 1408.3333 | per S.M. | 704.1667 | per S.M. | 563.3333 | per S.M.
| APPLY INSULATION | 0.1 | S.M.per hour | 0.2 | S.M.per hour | 0.25 | S.M.per hour | 586.8056 | per S.M. | 293.4028 | per S.M. | 234.7222 | per S.M.
| APPLY SHEET METAL COVER | 0.1 | S.M.per hour | 0.2 | S.M.per hour | 0.25 | S.M.per hour | 586.8056 | per S.M. | 293.4028 | per S.M. | 234.7222 | per S.M.
| PUMPS, COMPRESSORS & TURBINES | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FABRICATE | 0.029412 | S.M.per hour | 0.058824 | S.M.per hour | 0.073529 | S.M.per hour | 1995.1389 | per S.M. | 997.5694 | per S.M. | 798.0556 | per S.M.
| APPLY | 0.016667 | S.M.per hour | 0.033333 | S.M.per hour | 0.041667 | S.M.per hour | 3520.8333 | per S.M. | 1760.4167 | per S.M. | 1408.3333 | per S.M.
| PIPINGS AND COMPONENT INSULATION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIELD FABRICATE | 0.125 | FLG.per hour | 0.25 | FLG.per hour | 0.3125 | FLG.per hour | 469.4444 | per FLG. | 234.7222 | per FLG. | 187.7778 | per FLG.
| FIELD FABRICATESHEET METAL COVER | 0.625 | S.M.per hour | 1.25 | S.M.per hour | 1.5625 | S.M.per hour | 93.8889 | per S.M. | 46.9444 | per S.M. | 37.5556 | per S.M.
| APPLY INSULATION | 0.18519 | L.M.per hour | 0.37037 | L.M.per hour | 0.46296 | L.M.per hour | 316.875 | per L.M. | 158.4375 | per L.M. | 126.75 | per L.M.
| APPLY SHEET METAL COVER OR METAL COVER | 0.33333 | EACHper hour | 0.66667 | EACHper hour | 0.83333 | EACHper hour | 176.0417 | per EACH | 88.0208 | per EACH | 70.4167 | per EACH
| FABRICATE INSTRUMENT COVER | 0.0625 | EACHper hour | 0.125 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 469.4444 | per EACH | 375.5556 | per EACH
| INSTALL INSTRUMENT COVER | 0.083333 | EACHper hour | 0.16667 | EACHper hour | 0.20833 | EACHper hour | 704.1667 | per EACH | 352.0833 | per EACH | 281.6667 | per EACH
| INSULATE PIPE HANGERS | 0.125 | EACHper hour | 0.25 | EACHper hour | 0.3125 | EACHper hour | 469.4444 | per EACH | 234.7222 | per EACH | 187.7778 | per EACH
| FOR STREAM TRACED LINES | 0.13514 | L.M.per hour | 0.27027 | L.M.per hour | 0.33784 | L.M.per hour | 434.2361 | per L.M. | 217.1181 | per L.M. | 173.6944 | per L.M.
| REMOVAL OF OLD OR EXISTING INSTALLATION | 0.33333 | L.M.per hour | 0.66667 | L.M.per hour | 0.83333 | L.M.per hour | 176.0417 | per L.M. | 88.0208 | per L.M. | 70.4167 | per L.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
M. | TRADE:FIRE PROOFING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTALL STUDS | 1 | EACHper hour | 2 | EACHper hour | 2.5 | EACHper hour | 58.6806 | per EACH | 29.3403 | per EACH | 23.4722 | per EACH
| INSTALL MESH | 0.41667 | S.M.per hour | 0.83333 | S.M.per hour | 1.0417 | S.M.per hour | 140.8333 | per S.M. | 70.4167 | per S.M. | 56.3333 | per S.M.
| POURED | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FORMING | 0.035714 | S.M.per hour | 0.071429 | S.M.per hour | 0.089286 | S.M.per hour | 1643.0556 | per S.M. | 821.5278 | per S.M. | 657.2222 | per S.M.
| STRIP FORMS | 0.083333 | S.M.per hour | 0.16667 | S.M.per hour | 0.20833 | S.M.per hour | 704.1667 | per S.M. | 352.0833 | per S.M. | 281.6667 | per S.M.
| POUR CONCRETE | 0.0071429 | S.M.per hour | 0.014286 | S.M.per hour | 0.017857 | S.M.per hour | 8215.2778 | per S.M. | 4107.6389 | per S.M. | 3286.1111 | per S.M.
| CURING/PATCHING | 0.83333 | S.M.per hour | 1.6667 | S.M.per hour | 2.0833 | S.M.per hour | 70.4167 | per S.M. | 35.2083 | per S.M. | 28.1667 | per S.M.
| FINISHING | 0.71429 | S.M.per hour | 1.4286 | S.M.per hour | 1.7857 | S.M.per hour | 82.1528 | per S.M. | 41.0764 | per S.M. | 32.8611 | per S.M.
| TROWEL, PLASTERED | 0.18519 | S.M.per hour | 0.37037 | S.M.per hour | 0.46296 | S.M.per hour | 316.875 | per S.M. | 158.4375 | per S.M. | 126.75 | per S.M.
| PNEUMATIC APPLICATION | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| GUNITE | 0.41667 | S.M.per hour | 0.83333 | S.M.per hour | 1.0417 | S.M.per hour | 140.8333 | per S.M. | 70.4167 | per S.M. | 56.3333 | per S.M.
| APPLY FINEBRICK OR BLOCK | 0.625 | PC.per hour | 1.25 | PC.per hour | 1.5625 | PC.per hour | 93.8889 | per PC. | 46.9444 | per PC. | 37.5556 | per PC.
| REMOVAL OF EXISTING OR OLD FIREPROOFING | 0.2 | S.M.per hour | 0.4 | S.M.per hour | 0.5 | S.M.per hour | 293.4028 | per S.M. | 146.7014 | per S.M. | 117.3611 | per S.M.
| APPLY FIREPROOFING PAINT | 0.16667 | S.M.per hour | 0.33333 | S.M.per hour | 0.41667 | S.M.per hour | 352.0833 | per S.M. | 176.0417 | per S.M. | 140.8333 | per S.M.
| FIRE PROTERCTION: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| FIRE PROTECTION EQUIPMENT INSTALLATION: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| MONITOR | 0.1 | EACHper hour | 0.2 | EACHper hour | 0.25 | EACHper hour | 586.8056 | per EACH | 293.4028 | per EACH | 234.7222 | per EACH
| HOSE REELS AND CARTS | 0.033333 | EACHper hour | 0.066667 | EACHper hour | 0.083333 | EACHper hour | 1760.4167 | per EACH | 880.2083 | per EACH | 704.1667 | per EACH
| FIRE EXTINGUISHERS | 0.1 | EACHper hour | 0.2 | EACHper hour | 0.25 | EACHper hour | 586.8056 | per EACH | 293.4028 | per EACH | 234.7222 | per EACH
| PERSONAL EQUIPMENT: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| EYE WASH | 0.05 | EACHper hour | 0.1 | EACHper hour | 0.125 | EACHper hour | 1173.6111 | per EACH | 586.8056 | per EACH | 469.4444 | per EACH
| SAFETY SHOWERS | 0.05 | EACHper hour | 0.1 | EACHper hour | 0.125 | EACHper hour | 1173.6111 | per EACH | 586.8056 | per EACH | 469.4444 | per EACH
| BREATHING APPARATUS | 0.1 | EACHper hour | 0.2 | EACHper hour | 0.25 | EACHper hour | 586.8056 | per EACH | 293.4028 | per EACH | 234.7222 | per EACH
| SPRINKLER SYSTEM | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| SPRAY NOZZLES | 0.5 | EACHper hour | 1 | EACHper hour | 0.0125 | EACHper hour | 117.3611 | per EACH | 58.6806 | per EACH | 4694.4444 | per EACH
| WATER CANNONS | 0.1 | EACHper hour | 0.2 | EACHper hour | 0.25 | EACHper hour | 586.8056 | per EACH | 293.4028 | per EACH | 234.7222 | per EACH
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
N. | TRADE:PERMANENT FENCING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| INSTALL FENCE | 0.41667 | L.M.per hour | 0.83333 | L.M.per hour | 1.0417 | L.M.per hour | 140.8333 | per L.M. | 70.4167 | per L.M. | 56.3333 | per L.M.
| INSTALL GATES | 0.16667 | L.M.per hour | 0.33333 | L.M.per hour | 0.41667 | L.M.per hour | 352.0833 | per L.M. | 176.0417 | per L.M. | 140.8333 | per L.M.
| TO RAIL | 1.6667 | L.M.per hour | 3.3333 | L.M.per hour | 4.1667 | L.M.per hour | 35.2083 | per L.M. | 17.6042 | per L.M. | 14.0833 | per L.M.
| BARBE WIRE, 3 STRANDS | 1.6667 | L.M.per hour | 3.3333 | L.M.per hour | 4.1667 | L.M.per hour | 35.2083 | per L.M. | 17.6042 | per L.M. | 14.0833 | per L.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
O. | TRADE:PAINTING WORKS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| NEW STRUCTURAL STEEL | 0.05 | TONper hour | 1 | TONper hour | 0.11111 | TONper hour | 1173.6111 | per TON | 58.6806 | per TON | 528.125 | per TON
| OLD STRUCTURAL STEEL | 0.90909 | S.M.per hour | 1.8182 | S.M.per hour | 0.022727 | S.M.per hour | 64.5486 | per S.M. | 32.2743 | per S.M. | 2581.9444 | per S.M.
| NEW FLAT FLAT PLATES | 1.5625 | S.M.per hour | 3.125 | S.M.per hour | 0.038462 | S.M.per hour | 37.5556 | per S.M. | 18.7778 | per S.M. | 1525.6944 | per S.M.
| SURFACE PREPARATION: | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| IN TERMS OF WEIGHT | 0.0625 | TONper hour | 0.125 | TONper hour | 0.15625 | TONper hour | 938.8889 | per TON | 469.4444 | per TON | 375.5556 | per TON
| IN TERMS OF AREA | 1.1628 | S.M.per hour | 0.033333 | S.M.per hour | 2.9412 | S.M.per hour | 50.4653 | per S.M. | 1760.4167 | per S.M. | 19.9514 | per S.M.
| SAND PREPARATION | 0.016667 | TONper hour | 0 | TONper hour | 0.041667 | TONper hour | 3520.8333 | per TON | 0 | per TON | 1408.3333 | per TON
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
P. | TRADE:HEATING VENTILATING AND CONDITIONING | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| HEAVY PIPING | 0.14286 | L.M.per hour | 0.28571 | L.M.per hour | 0.35714 | L.M.per hour | 410.7639 | per L.M. | 205.3819 | per L.M. | 164.3056 | per L.M.
| DUCT WORK INSTALL | 0.083333 | S.M.per hour | 0.16667 | S.M.per hour | 0.20833 | S.M.per hour | 704.1667 | per S.M. | 352.0833 | per S.M. | 281.6667 | per S.M.
| DUCT WORK FAB. | 0.027778 | S.M.per hour | 0.055556 | S.M.per hour | 0.069444 | S.M.per hour | 2112.5 | per S.M. | 1056.25 | per S.M. | 845 | per S.M.
| PACKAGE UNIT AIR CONDITIONER | 0.020833 | EACHper hour | 0.041667 | EACHper hour | 0.052083 | EACHper hour | 2816.6667 | per EACH | 1408.3333 | per EACH | 1126.6667 | per EACH
| UNIT HEATER | 0.041667 | EACHper hour | 0.083333 | EACHper hour | 0.10417 | EACHper hour | 1408.3333 | per EACH | 704.1667 | per EACH | 563.3333 | per EACH
| FINNED CONVERTER | 0.1 | EACHper hour | 0.2 | EACHper hour | 0.25 | EACHper hour | 586.8056 | per EACH | 293.4028 | per EACH | 234.7222 | per EACH
| EXHAUST FAN PROPELLER | 0.0625 | EACHper hour | 0.125 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 469.4444 | per EACH | 375.5556 | per EACH
| GRAVITY ROOF PAINT | 0.071429 | L.M.per hour | 0.13699 | L.M.per hour | 0.17123 | L.M.per hour | 821.5278 | per L.M. | 428.3681 | per L.M. | 342.6944 | per L.M.
| POWER ROOF VENT | 0.020833 | EACHper hour | 0.041667 | EACHper hour | 0.052083 | EACHper hour | 2816.6667 | per EACH | 1408.3333 | per EACH | 1126.6667 | per EACH
| ROUND ROOF VENT | 0.0625 | EACHper hour | 0.125 | EACHper hour | 0.15625 | EACHper hour | 938.8889 | per EACH | 469.4444 | per EACH | 375.5556 | per EACH
| PLUMBING PIPING | 0.14286 | L.M.per hour | 0.28571 | L.M.per hour | 0.35714 | L.M.per hour | 410.7639 | per L.M. | 205.3819 | per L.M. | 164.3056 | per L.M.
|  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Q. | MISCELLANEOUS | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| WATER STOP INSTALLATION | 0.74627 | L.M.per hour | 1.4925 | L.M.per hour | 1.8519 | L.M.per hour | 78.6319 | per L.M. | 39.316 | per L.M. | 31.6875 | per L.M.
| CAULKING SLAB JOINT | 2.5 | L.M.per hour | 5 | L.M.per hour | 6.25 | L.M.per hour | 23.4722 | per L.M. | 11.7361 | per L.M. | 9.3889 | per L.M.
| ASPHALTING | 0.625 | S.M.per hour | 1.25 | S.M.per hour | 1.5625 | S.M.per hour | 93.8889 | per S.M. | 46.9444 | per S.M. | 37.5556 | per S.M.
| GROUTNG AND TOOL PLASTERING | 0.2994 | S.M.per hour | 0.5988 | S.M.per hour | 1.1905 | S.M.per hour | 195.9931 | per S.M. | 97.9965 | per S.M. | 49.2917 | per S.M.
| WATER PROOFING RUBBERIZED | 0.90909 | S.M.per hour | 1.8182 | S.M.per hour | 3.5714 | S.M.per hour | 64.5486 | per S.M. | 32.2743 | per S.M. | 16.4306 | per S.M.
| COPPER CLADDING ROOF DECK | 1 | L.M.per hour | 2 | L.M.per hour | 4 | L.M.per hour | 58.6806 | per L.M. | 29.3403 | per L.M. | 14.6701 | per L.M.
| WATER PROOFING FLINKOTE | 1.8519 | S.M.per hour | 3.7037 | S.M.per hour | 7.1429 | S.M.per hour | 31.6875 | per S.M. | 15.8438 | per S.M. | 8.2153 | per S.M.
| DEMOLITION OF ADOBE WALL | 0.3125 | CU.M.per hour | 0.625 | CU.M.per hour | 1.25 | CU.M.per hour | 187.7778 | per CU.M. | 93.8889 | per CU.M. | 46.9444 | per CU.M.
| PAINTING | 1.4706 | S.M.per hour | 2.9412 | S.M.per hour | 5.8824 | S.M.per hour | 39.9028 | per S.M. | 19.9514 | per S.M. | 9.9757 | per S.M.
| COPPER WATER STOP CUT AND SHAPE | 0.090909 | L.M.per hour | 0.16667 | L.M.per hour | 33.3333 | L.M.per hour | 645.4861 | per L.M. | 352.0833 | per L.M. | 1.7604 | per L.M.
| COPPER WATER STOP CUT AND INSTALLATION | 0.045455 | L.M.per hour | 0.090909 | L.M.per hour | 16.6667 | L.M.per hour | 1290.9722 | per L.M. | 645.4861 | per L.M. | 3.5208 | per L.M.
| SETTING ANCHOR BOLT | 0.010309 | KGper hour | 0.020408 | KGper hour | 4.1667 | KGper hour | 5692.0139 | per KG | 2875.3472 | per KG | 14.0833 | per KG
| SETTING ANCHOR BOXES | 0.27473 | CU.M.per hour | 0.54945 | CU.M.per hour | 1.0989 | CU.M.per hour | 213.5972 | per CU.M. | 106.7986 | per CU.M. | 53.3993 | per CU.M.

## MANHOUR EQUIVALENT
MANHOUR EQUIVALENT RATE |  |  |  |  | Table of Rates
[5 empty] | Area | Position
[6 empty] | Foreman | Skilled | Labor
[5 empty] | NCR | 926.25 | 748.125 | 570
[5 empty] | CAR | 650 | 525 | 400 | 1.3125
[5 empty] | Region 1 | 650 | 525 | 400 | 1.625
[5 empty] | Region 2 | 650 | 525 | 400
[5 empty] | Region 3 | 747.5 | 603.75 | 460
|  | (Drop-Down List) |  |  | Region 4A | 763.75 | 616.875 | 470
CHOOSE RATE : |  | CAR | Total Daily Rate | Hourly Pay | Region 4B | 576.875 | 465.9375 | 355
Position | Quantity | Rate |  |  | Region 5 | 593.125 | 479.0625 | 365
Foreman | 1 | 650 | 650 | 81.25 | Region 6 | 731.25 | 590.625 | 450
Skilled | 3 | 525 | 1575 | 196.875 | Region 7 | 706.875 | 570.9375 | 435
Labor | 5 | 400 | 2000 | 250 | Region 8 | 609.375 | 492.1875 | 375
|  |  | Total Rate per Manhour = | 58.6806 | Region 9 | 570.375 | 460.6875 | 351
[5 empty] | Region 10 | 658.125 | 531.5625 | 405
NOTE : You can change the quantities of the manpower per position and their respective rates in the Table. |  |  |  |  | Region 11 | 719.875 | 581.4375 | 443
[5 empty] | Region 12 | 598 | 483 | 368
[5 empty] | Region 13 | 568.75 | 459.375 | 350
[5 empty] | BARMM | 554.125 | 447.5625 | 341

## LABOR CALCULATOR
ACTIVITIES |  | INPUT HERE |  | choose labor productivity rate BELOW | TOTAL COST
LABOR PRODUCTIVITY
ITEM NO. | WORK DESCRIPTION | QUANTITY | UNIT | FAST
RATE PER UNIT
|  | SLOW | AVERAGE | FAST
A. | FORM WORKS INSTALLATION
| WALL ON THE GROUND | 20 | SQ.M. | 93.8889 | 1877.7778
| WALL ABOVER GROUND | 20 | SQ.M. | 110.3194 | 2206.3889
| BEAMS |  | SQ.M. | 144.3542 | 0
| COLUMN |  | SQ.M. | 110.3194 | 0
| SUSPENDED SLAB |  |  | 0 | 0
| 0 TO 18' |  | SQ.M. | 78.6319 | 0
| 18' TO 36' UP |  | SQ.M. | 156.0903 | 0
| ELEVATED AND SHORED SLAB FORMING |  |  | 0 | 0
| FORMING ONLY |  | SQ.M. | 403.7222 | 0
| FORMING AND SHORING |  | SQ.M. | 516.3889 | 0
| WOOD WALL AND PARTITION |  | SQ.M. | 23.4722 | 0
|  |  |  | 0 | 0
B. | FORMWORKS FABRICATION |  | SQ.M. | 50.4653 | 0
|  |  |  | 0 | 0
C. | STRIPPING OF FORMS |  |  | 0 | 0
| WALL ON GROUND |  | SQ.M. | 11.7361 | 0
| WALL ABOVE 10' |  | SQ.M. | 60.441 | 0
| BEAMS |  | SQ.M. | 48.1181 | 0
| COLUMNS |  | SQ.M. | 39.9028 | 0
| SUSPENDED SLAB |  | SQ.M. | 0 | 0
| 0 TO 18' |  | SQ.M. | 39.316 | 0
| 18' TO 36' UP |  | SQ.M. | 50.4653 | 0
| ELEVATED AND SHORED SLAB FORMING |  | SQ.M. | 0 | 0
| STRIP OF FORMS |  | SQ.M. | 164.3056 | 0
| FLOOR SLAB AT GRADE STRIP OF FORMS |  | SQ.M. |  | #VALUE!
|  |  |  | 0 | 0
D | INSTALLION OF CARPENTRY WORKS |  |  | 0 | 0
| PLYWOOD PARTITION |  | PC | 46.9444 | 0
| T & G FLOORING AND SHORING |  | B.F. | 6.4549 | 0
| CEILING FRAME |  | B.F. | 17.0174 | 0
| SIDING FRAME |  | B.F. | 12.3229 | 0
| FLOORING FRAME |  | B.F. | 45.184 | 0
| WOODEN POSS ERECTION |  | B.F. | 19.9514 | 0
| TRUSS FABRICATION |  | B.F. | 16.4306 | 0
| TRUSS INSTALLATION |  | B.F. | 37.5556 | 0
| GIRTS INSTALLTION |  | B.F. | 9.9757 | 0
| PLATES INSTALLATION |  | B.F. | 6.4549 | 0
| PURLINS INSTALLATION |  | B.F. | 5.8681 | 0
| FASCIA BOARD INSTALLATION |  | B.F. | 21.125 | 0
| 1/4" or 3/4" thk PLYWOOD |  |  | 0 | 0
| CUTTING BY MANUAL |  | PC | 46.9444 | 0
| ASSEMBLY |  | S.F. | 19.3646 | 0
| CEILNG: |  |  | 0 | 0
| FRAME INSTALLATION |  | SQ.M. | 62.2014 | 0
| PLYWOOD INSTALLLATION |  | SQ.M. | 52.8125 | 0
| CABINET BOARDING |  | B.F. | 5.8681 | 0
| CABINET FRAMING |  | B.F. | 8.2153 | 0
| WOOD WALL PARTITION |  | SQ.M. | 23.4722 | 0
| PANEL WALL |  | SQ.M. | 328.6111 | 0
| FORMING WEIGHT ANCHOR BOLT |  | SQ.M. | 211.25 | 0
| WET FORMING |  | SQ.M. | 164.3056 | 0
|  |  |  | 0 | 0
E. | DOORS AND WINDOWS |  |  | 0 | 0
| W-PANEL INSTALLATION |  | PC. | 18.7778 | 0
| STEEL WINDOWS INSTALLATION |  | PC. | 93.8889 | 0
| LOUVER WINDOWS INSTALLATION: |  |  | 0 | 0
| FIXED ASBESTOS |  | SQ.M. | 217.1181 | 0
| FIXED METAL LOUVERS |  | SQ.M. | 146.7014 | 0
| FIXED GI SHEETS |  | SQ.M. | 217.1181 | 0
| FIXED GLASS |  | SQ.M. | 146.7014 | 0
| FIXED WOODEN |  | SQ.M. | 158.4375 | 0
| ALUMINUM FRAME WINDOWS |  | EACH | 469.4444 | 0
| SLIDING GLASS DOOR |  | EACH | 563.3333 | 0
| HOLLOW METAL DOOR |  | EACH | 469.4444 | 0
| ROLLING DOORS |  | EACH | 1173.6111 | 0
| FIXED WINDOW |  | S.F. | 14.6701 | 0
| DOOR LOCKSET |  | SET | 75.1111 | 0
| DOOR JAMB FABRICATION |  | B.F. | 10.5625 | 0
| DOOR JAMB INSTALLATION |  | B.F. | 15.2569 | 0
| CYCLONE WIRE INSTALLATION |  | SQ.M. | 146.7014 | 0
|  |  |  | 0 | 0
F. | TRADE MASONRY WORKS |  |  | 0 | 0
| GROUTING and TOL PLASTERING |  | SQ.M. | 78.6319 | 0
| PEBBLE FINISHED |  | SQ.M. | 78.6319 | 0
| MABLE INSTALLATION |  | SQ.M. | 93.8889 | 0
| 1/4" x 2' x 8" RED BRICKS |  | SQ.M. | 234.7222 | 0
| GLAZED TILES |  | SQ.M. | 494.0903 | 0
| UNGLAZED TILES |  | SQ.M. | 204.2083 | 0
| GLAZED TILE WALL |  | SQ.M. | 140.8333 | 0
| CONC. BLOCK INT. WALL |  | SQ.M. | 211.25 | 0
| CONC. BLOCK EXT. WALL |  | SQ.M. | 187.7778 | 0
| BRICKWORK |  | SQ.M. | 23.4722 | 0
| PLASTER WALL AND CEILING |  | SQ.M. | 199.5139 | 0
| HOLLOW TILE WALL |  | SQ.M. | 93.8889 | 0
| ACOUSTICAL TILE WALL |  | SQ.M. | 56.3333 | 0
| VINYL FLOOR TILE |  | SQ.M. | 84.5 | 0
| UNGLAZED OR MOSAIC FLOOR TILE |  | SQ.M. | 399.0278 | 0
| LAYING OF CHB & ADOBE |  | SQ.M. | 53.3993 | 0
| CEMENT FINISH |  | SQ.M. | 33.4479 | 0
| CONC. HOLLOW BLOCK LAYING: |  |  | 0 | 0
| 6" CHB |  | SQ.M. | 75.1111 | 0
| 4" CHB | 161.7 | SQ.M. | 62.2014 | 10057.9646
| 8" CHB |  | SQ.M. | 93.8889 | 0
| VIT. TILES FLOOR |  | SQ.M. | 249.9792 | 0
| VIT. TILES WALL |  | SQ.M. | 280.4931 | 0
|  |  |  | 0 | 0
G. | TINSMITHING WORK |  |  | 0 | 0
| CORR GI SHEETS: |  |  | 0 | 0
| LIFTING |  | SQ.M. | 50.4653 | 0
| INSTALLATION |  | SQ.M. | 143.7674 | 0
| INSTALLATION OF ASBESTOS ROOFING |  | SHT. | 46.9444 | 0
| INSTALLATION OF ALUMINUM GI SHEET |  | SHT. | 37.5556 | 0
| COPPER CLADDING ROOF DECK |  | L.M. | 23.4722 | 0
| FAB, GI GUTTER |  | SHT. | 163.1319 | 0
| GI SHEET ROOFING |  | SHT. | 38.7292 | 0
| FAB OF GI GUTTER |  | L.M. | 24.6458 | 0
| FAB. GI DOWNSPOUT |  | L.M. | 104.4514 | 0
| GUTTER CUT & SHAPE |  | L.M. | 7.6285 | 0
| INST. OF GUTTER |  | L.M. | 41.6632 | 0
| DOWNSPOUT CUT AND SHAPE |  | L.M. | 14.0833 | 0
| DOWNSPOUT INSTALLATION |  | L.M. | 6.4549 | 0
| CORR. GI ROOFING |  | SQ.M. | 84.5 | 0
| CORR ALUMINUM ROOFING |  | SQ.M. | 84.5 | 0
| BUILT UP ROOFING 4 PLY |  | SQ.M. | 399.0278 | 0
| PROTECTED METAL |  | SQ.M. | 93.8889 | 0
| CORR. ASBESTOS INST., LIFTING & HAULING |  | SQ.M. | 79.8056 | 0
| LEADERS & GUTTERS |  | SQ.M. | 28.1667 | 0
|  |  |  | 0 | 0
H | CONCRETE AND REBAR WORKS |  |  | 0 | 0
| PLACING CONCRETE: |  |  | 0 | 0
| SLAB ON FILL |  | CU.M. | 234.7222 | 0
| SLIP FORM |  | CU.M. | 1173.6111 | 0
| FLR FINISH UNHARDENED |  | SQ.M. | 46.9444 | 0
| CONC. FINISH HARDENED |  | SQ.M. | 66.8958 | 0
| REBAR WORKS: |  |  | 0 | 0
| GROUND FLR. INSTALLATION |  | KGS | 3.5208 | 0
| UPPER FLR. INSTALLATION |  | KGS | 3.5208 | 0
| FABRICATION |  | KGS | 4.6944 | 0
| MIXING MANUAL |  | CU.M. | 751.1111 | 0
| MIXING MACHINE |  | CU.M. | 84.5 | 0
| MORE THAN 1.80 CU.M. POUR: |  |  | 0 | 0
| CHUTE FROM TRUCK |  | CU.M. | 328.6111 | 0
| CRANE AND BUCKET |  | CU.M. | 657.2222 | 0
| WHEELING |  | CU.M. | 1267.5 | 0
| FINISHING |  | SQ.M. | 131.4444 | 0
| CONCRETE POUR ON ELEVATED AND SHORED |  |  | 0 | 0
| SLAB FORMING CHUTE & BUCKET |  | CU.M. | 985.8333 | 0
| PLACEMENT OF REBARS ON FOOTING |  | KGS | 24.6458 | 0
| FIELD FABRICATION OF REBARS |  | KGS | 15.2569 | 0
|  |  |  | 0 | 0
I. | EARTH WORKS |  |  | 0 | 0
| MACHINE EXCAVATION: |  |  | 0 | 0
| SAND |  | CU.M. | 28.1667 | 0
| SAND AND MARL |  | CU.M. | 37.5556 | 0
| MARL |  | CU.M. | 51.6389 | 0
| GRANULAR BACKFILL |  | CU.M. | 56.3333 | 0
| GRANULAR SOIL BACKFILL |  | CU.M. | 70.4167 | 0
| MANUAL FOUNDATION EXCAVATION & BACKFILL: |  |  | 0 | 0
| SAND |  | CU.M. | 187.7778 | 0
| EXCAVATION OF SAND &MARL |  | CU.M. | 305.1389 | 0
| EXCAVATION OF MARL |  | CU.M. | 492.9167 | 0
| BACKFILL OF SAND |  | CU.M. | 258.1944 | 0
| BACKFILL OF SAND &MARL |  | CU.M. | 375.5556 | 0
| BACKFILL OF MARL |  | CU.M. | 563.3333 | 0
| FLOOR SLAB & GRADE: |  |  | 0 | 0
| GRADING MANUAL |  | SQ.M. | 61.0278 | 0
| EXCAVATION AND BACKFILL |  | CU.M. | 845 | 0
| FINE GRADING & FINISHING |  |  | 0 | 0
| GRADING MANUAL |  | SQ.M. | 21.125 | 0
| FINISHING SOIL SURFACE |  | SQ.M. | 25.8194 | 0
| DIKES |  | CU.M. | 56.3333 | 0
J | ROAD WORKS |  |  | 0 | 0
| BASE COURSE |  | SQ.M. | 5.8681 | 0
| CURBS & GUTTER |  | CU.M. | 84.5 | 0
| 4" THK ROAD |  | SQ.M. | 61.0278 | 0
| 6" THK ROAD |  | SQ.M. | 65.7222 | 0
| 8" THK ROAD |  | SQ.M. | 70.4167 | 0
| TROWEL FINISH |  | SQ.M. | 15.2569 | 0
| SPECIAL TOPPING |  | SQ.M. | 56.3333 | 0
| 4" STONE OR SHELL ROAD |  | SQ.M. | 15.2569 | 0
| 6" STONE OR SHELL ROAD |  | SQ.M. | 19.9514 | 0
| 8" STONE OR SHELL ROAD |  | SQ.M. | 24.6458 | 0
| ACID PROOFING |  | CU.M. | 28.1667 | 0
| ASPHALT PAVING: |  |  | 0 | 0
| FINE GRADING & FINISHING |  | SQ.M. | 19.9514 | 0
| PLACE BASE COURSE |  | SQ.M. | 9.3889 | 0
| ASPHALT |  | SQ.M. | 9.3889 | 0
| ACID BLOCK OR PAVING BLOCK: |  |  | 0 | 0
| FIND GRADING |  | SQ.M. | 19.9514 | 0
| INSTALL BRICK |  | SQ.M. | 197.1667 | 0
| CRUSH STONE OR SHELL SURFACING |  |  | 0 | 0
| FINE GRADING |  | SQ.M. | 15.2569 | 0
| PLACE SPREAD AND COMPACT STONE TO 4" |  | SQ.M. | 19.9514 | 0
| OVER 9" THK |  | SQ.M. | 24.6458 | 0
| TANK CUSHION |  |  | 0 | 0
| SAND CUSHION |  | CU.M. | 32.8611 | 0
| APHALT RETAINER RING |  | SQ.M. | 9.3889 | 0
| NON GRANULAR BACKFILL |  | CU.M. | 93.8889 | 0
| EXCAVATION MANUAL: |  |  | 0 | 0
| COMMON EARTH |  | CU.M. | 375.5556 | 0
| LOAN OF SAND |  | CU.M. | 61.6146 | 0
| CLAY OR HEAVY SOIL ROCK |  | CU.M. | 76.8715 | 0
| ROCK |  | CU.M. | 123.2292 | 0
| MECHANICAL EXCAVATION |  |  | 0 | 0
| COMMON EARTH |  | CU.M. | 313.3542 | 0
| ROCK W/ JACKHAMMER |  | CU.M. | 782.7986 | 0
| BACKFILLING |  |  | 0 | 0
| COMMON MANUAL |  | CU.M. | 38.7292 | 0
| GRAVEL FILL MANUAL |  | CU.M. | 234.7222 | 0
| TRENCHING AND BACKFILLING OF UNDERGROUND |  |  | 0 | 0
| PIPING USING EXCAVATION MATERIALS MANUAL |  |  | 0 | 0
| FROM 0 TO 2 MTRS. DEPTH |  | L.M. | 58.6806 | 0
| 2 TO 3 |  | L.M. | 137.3125 | 0
| 3 TO 4 |  | L.M. | 117.3611 | 0
| 4 TO 5 |  | L.M. | 156.0903 | 0
| PLACING BINDER GRAVEL |  | CU.M. | 4.6944 | 0
| ESCOMBRO BACKFILLING |  | CU.M. | 9.9757 | 0
| SPREADING, TAMPING AND GRADING |  | SQ.M. | 22.2986 | 0
| MECHANICAL COMPACTION, PLATE COMPACTION |  | CU.M. | 2.3472 | 0
| MANUAL CLEARING AND GRUBBING |  |  | 0 | 0
| CLEARING UNDERGROWTH AND TREES 12" |  | SQ.M. | 2.3472 | 0
| CLEARING UNDERGROWTH AND SHRUBS |  | SQ.M. | 1.1736 | 0
| DISPOSAL OF SOIL |  | CU.M. | 79.2188 | 0
| MAULING OF SOIL |  | CU.M. | 46.9444 | 0
| GRAVEL FILL |  | CU.M. | 97.4097 | 0
| EXCAVATION CRANE AND CLAMPSHELL |  |  | 0 | 0
. | WITH 8-MEN AND 2 CARPENTERS |  | CU.M. | 50.4653 | 0
|  |  |  | 0 | 0
K. | TRADE: UNDERGROUND PIPING AND PLUMBING WORKS |  |  | 0 | 0
1 | LAYING ASBESTOS PIPES: |  |  | 0 | 0
| 1//2Ø |  | L.M. | 31.1007 | 0
| 3/4" Ø |  | L.M. | 31.1007 | 0
| 1 1/4" |  | L.M. | 34.6215 | 0
| 1 1/2 TO 2" Ø |  | L.M. | 38.7292 | 0
| 2 1/2" Ø |  | L.M. | 41.0764 | 0
| 3" Ø |  | L.M. | 50.4653 | 0
| 3 1/2" Ø |  | L.M. | 53.9861 | 0
| 4" Ø |  | L.M. | 62.2014 | 0
2 | CAST IRON PIPE |  |  | 0 | 0
| 2" Ø |  | L.M. | 102.691 | 0
| 4" Ø |  | L.M. | 154.3299 | 0
| 6" Ø |  | L.M. | 231.2014 | 0
| 8" Ø |  | L.M. | 308.6597 | 0
| 10" Ø |  | L.M. | 468.2708 | 0
| 12" Ø |  | L.M. | 484.1146 | 0
| 14" Ø |  | L.M. | 565.6806 | 0
| 16" Ø |  | L.M. | 642.5521 | 0
| 18" Ø |  | L.M. | 720.0104 | 0
| 20" Ø |  | L.M. | 771.0625 | 0
| 24" Ø |  | L.M. | 848.5208 | 0
| 30" Ø |  | L.M. | 964.1215 | 0
3 | LAYING PVC PIPE |  |  | 0 | 0
| 1/2 TO 3/4" Ø |  | L.M. | 8.8021 | 0
| 1 TO 1 1/4" Ø |  | L.M. | 34.6215 | 0
| 1 1/2 TO 2" Ø |  | L.M. | 38.7292 | 0
| 2 1/2" Ø |  | L.M. | 45.7708 | 0
| 3" Ø |  | L.M. | 50.4653 | 0
| 4" Ø |  | L.M. | 61.6146 | 0
| 5" Ø |  | L.M. | 76.8715 | 0
| 6" Ø |  | L.M. | 115.6007 | 0
4 | LAYING RCP 8 MEN (1 TEAM) |  |  | 0 | 0
| 24"Ø |  | L.M. | 187.7778 | 0
| 36"Ø |  | L.M. | 300.4444 | 0
| 48"Ø |  | L.M. | 501.1319 | 0
| 6-18"Ø |  | L.M. | 62.2014 | 0
|  |  |  | 0 | 0
| LAVATORY |  | EACH | 375.5556 | 0
| WATER CLOSET |  | EACH | 563.3333 | 0
| URINAL UTILITY STALL |  | EACH | 1126.6667 | 0
| URINAL PEDESTRAL TYPE |  | EACH | 751.1111 | 0
| SHOWER AND INSTALL |  | EACH | 469.4444 | 0
| 5 MAN GROUP SHOWER |  | EACH | 1690 | 0
| BAH TUBS |  | EACH | 1126.6667 | 0
| SLOPE SINK |  | EACH | 657.2222 | 0
| HOT WATER HEATER |  | EACH | 657.2222 | 0
| 16 PERSON WASH SINK |  | EACH | 1220.5556 | 0
| DRINKING FOUNTAIN |  | EACH | 610.2778 | 0
| EYE WASH |  | EACH | 375.5556 | 0
| MISC. FIXTURES |  | EACH | 93.8889 | 0
| PARTITIONS |  | EACH | 375.5556 | 0
| LAYING OF 24"Ø RCP |  | PIPE | 187.7778 | 0
| LAYING OF 36"Ø RCP |  | PIPE | 300.4444 | 0
| LAYING OF 48"Ø RCP |  | PIPE | 500.5451 | 0
|  |  |  | 0 | 0
L. | TRADE INSULATION |  |  | 0 | 0
| EQUIPMENT INSTALLATION |  |  | 0 | 0
| VESSEL, EXCHANGE & TANKS |  |  | 0 | 0
| FIELD FABRICATION INSULATION |  | S.M. | 117.3611 | 0
| FIELD FABRICATION SHEET METAL COVER |  | S.M. | 563.3333 | 0
| APPLY INSULATION |  | S.M. | 234.7222 | 0
| APPLY SHEET METAL COVER |  | S.M. | 234.7222 | 0
| PUMPS, COMPRESSORS & TURBINES |  |  | 0 | 0
| FABRICATE |  | S.M. | 798.0556 | 0
| APPLY |  | S.M. | 1408.3333 | 0
| PIPINGS AND COMPONENT INSULATION |  |  | 0 | 0
| FIELD FABRICATE |  | FLG. | 187.7778 | 0
| FIELD FABRICATESHEET METAL COVER |  | S.M. | 37.5556 | 0
| APPLY INSULATION |  | L.M. | 126.75 | 0
| APPLY SHEET METAL COVER OR METAL COVER |  | EACH | 70.4167 | 0
| FABRICATE INSTRUMENT COVER |  | EACH | 375.5556 | 0
| INSTALL INSTRUMENT COVER |  | EACH | 281.6667 | 0
| INSULATE PIPE HANGERS |  | EACH | 187.7778 | 0
| FOR STREAM TRACED LINES |  | L.M. | 173.6944 | 0
| REMOVAL OF OLD OR EXISTING INSTALLATION |  | L.M. | 70.4167 | 0
|  |  |  | 0 | 0
M. | TRADE:FIRE PROOFING |  |  | 0 | 0
| INSTALL STUDS |  | EACH | 23.4722 | 0
| INSTALL MESH |  | S.M. | 56.3333 | 0
| POURED |  |  | 0 | 0
| FORMING |  | S.M. | 657.2222 | 0
| STRIP FORMS |  | S.M. | 281.6667 | 0
| POUR CONCRETE |  | S.M. | 3286.1111 | 0
| CURING/PATCHING |  | S.M. | 28.1667 | 0
| FINISHING |  | S.M. | 32.8611 | 0
| TROWEL, PLASTERED |  | S.M. | 126.75 | 0
| PNEUMATIC APPLICATION |  |  | 0 | 0
| GUNITE |  | S.M. | 56.3333 | 0
| APPLY FINEBRICK OR BLOCK |  | PC. | 37.5556 | 0
| REMOVAL OF EXISTING OR OLD FIREPROOFING |  | S.M. | 117.3611 | 0
| APPLY FIREPROOFING PAINT |  | S.M. | 140.8333 | 0
| FIRE PROTERCTION: |  |  | 0 | 0
| FIRE PROTECTION EQUIPMENT INSTALLATION: |  |  | 0 | 0
| MONITOR |  | EACH | 234.7222 | 0
| HOSE REELS AND CARTS |  | EACH | 704.1667 | 0
| FIRE EXTINGUISHERS |  | EACH | 234.7222 | 0
| PERSONAL EQUIPMENT: |  |  | 0 | 0
| EYE WASH |  | EACH | 469.4444 | 0
| SAFETY SHOWERS |  | EACH | 469.4444 | 0
| BREATHING APPARATUS |  | EACH | 234.7222 | 0
| SPRINKLER SYSTEM |  |  | 0 | 0
| SPRAY NOZZLES |  | EACH | 4694.4444 | 0
| WATER CANNONS |  | EACH | 234.7222 | 0
|  |  |  | 0 | 0
N. | TRADE:PERMANENT FENCING |  |  | 0 | 0
| INSTALL FENCE |  | L.M. | 56.3333 | 0
| INSTALL GATES |  | L.M. | 140.8333 | 0
| TO RAIL |  | L.M. | 14.0833 | 0
| BARBE WIRE, 3 STRANDS |  | L.M. | 14.0833 | 0
|  |  |  | 0 | 0
O. | TRADE:PAINTING WORKS |  |  | 0 | 0
| NEW STRUCTURAL STEEL |  | TON | 528.125 | 0
| OLD STRUCTURAL STEEL |  | S.M. | 2581.9444 | 0
| NEW FLAT FLAT PLATES |  | S.M. | 1525.6944 | 0
| SURFACE PREPARATION: |  |  | 0 | 0
| IN TERMS OF WEIGHT |  | TON | 375.5556 | 0
| IN TERMS OF AREA |  | S.M. | 19.9514 | 0
| SAND PREPARATION |  | TON | 1408.3333 | 0
|  |  |  | 0 | 0
P. | TRADE:HEATING VENTILATING AND CONDITIONING |  |  | 0 | 0
| HEAVY PIPING |  | L.M. | 164.3056 | 0
| DUCT WORK INSTALL |  | S.M. | 281.6667 | 0
| DUCT WORK FAB. |  | S.M. | 845 | 0
| PACKAGE UNIT AIR CONDITIONER |  | EACH | 1126.6667 | 0
| UNIT HEATER |  | EACH | 563.3333 | 0
| FINNED CONVERTER |  | EACH | 234.7222 | 0
| EXHAUST FAN PROPELLER |  | EACH | 375.5556 | 0
| GRAVITY ROOF PAINT |  | L.M. | 342.6944 | 0
| POWER ROOF VENT |  | EACH | 1126.6667 | 0
| ROUND ROOF VENT |  | EACH | 375.5556 | 0
| PLUMBING PIPING |  | L.M. | 164.3056 | 0
|  |  |  | 0 | 0
Q. | MISCELLANEOUS |  |  | 0 | 0
| WATER STOP INSTALLATION |  | L.M. | 31.6875 | 0
| CAULKING SLAB JOINT |  | L.M. | 9.3889 | 0
| ASPHALTING |  | S.M. | 37.5556 | 0
| GROUTNG AND TOOL PLASTERING |  | S.M. | 49.2917 | 0
| WATER PROOFING RUBBERIZED |  | S.M. | 16.4306 | 0
| COPPER CLADDING ROOF DECK |  | L.M. | 14.6701 | 0
| WATER PROOFING FLINKOTE |  | S.M. | 8.2153 | 0
| DEMOLITION OF ADOBE WALL |  | CU.M. | 46.9444 | 0
| PAINTING |  | S.M. | 9.9757 | 0
| COPPER WATER STOP CUT AND SHAPE |  | L.M. | 1.7604 | 0
| COPPER WATER STOP CUT AND INSTALLATION |  | L.M. | 3.5208 | 0
| SETTING ANCHOR BOLT |  | KG | 14.0833 | 0
| SETTING ANCHOR BOXES |  | CU.M. | 53.3993 | 0
|  |  | TOTAL LABOR COST = |  | #VALUE!

## CALCULATIONS (hidden)
| MANHOUR EQUIVALENT | [9 empty] | OUTPUT PER HOUR
| 58.6806 | per hour in area of CAR
EQUIVALENT LABOR COST
LOW | [7 empty] | MANHOURS PER QUANTITY (M.H./UNIT) |  |  | 3 WORKER PRODUCTIVITY RATE | [6 empty] | MANHOURS PER QUANTITY (M.H./UNIT)
AVERAGE | LOW | PESOS PER | AVERAGE | PESOS PER | HIGH | PESOS PER | UNIT | LOW | AVERAGE | HIGH | LOW | UNIT | AVERAGE | UNIT | HIGH | UNIT | UNIT | LOW | AVERAGE | HIGH
HIGH
| 234.7222 | per SQ.M. | 117.3611 | per SQ.M. | 93.8889 | per SQ.M. | SQ.M. | 4 | 2 | 1.6 | 0.25 | SQ.M. per hour | 0.5 | SQ.M. per hour | 0.625 | SQ.M. per hour | SQ.M. | 4 | 2 | 1.6 | per hour | per
| 275.7986 |  | 137.8993 |  | 110.3194 |  | SQ.M. | 4.7 | 2.35 | 1.88 | [6 empty] | SQ.M. | 4.7 | 2.35 | 1.88 | per hour | per
| 361.4722 |  | 180.7361 |  | 144.3542 |  | SQ.M. | 6.16 | 3.08 | 2.46 | [6 empty] | SQ.M. | 6.16 | 3.08 | 2.46 | per hour | per
| 275.7986 |  | 137.8993 |  | 110.3194 |  | SQ.M. | 4.7 | 2.35 | 1.88 | [6 empty] | SQ.M. | 4.7 | 2.35 | 1.88 | per hour | per
| 0 |  | 0 |  | 0
| 195.9931 |  | 97.9965 |  | 78.6319 |  | SQ.M. | 3.34 | 1.67 | 1.34 | [6 empty] | SQ.M. | 3.34 | 1.67 | 1.34 | per hour | per
| 390.8125 |  | 195.4062 |  | 156.0903 |  | SQ.M. | 6.66 | 3.33 | 2.66 | [6 empty] | SQ.M. | 6.66 | 3.33 | 2.66 | per hour | per
| 0 |  | 0 |  | 0
| 1009.3056 |  | 528.125 |  | 403.7222 |  | SQ.M. | 17.2 | 9 | 6.88 | [6 empty] | SQ.M. | 17.2 | 9 | 6.88 | per hour | per
| 1290.9722 |  | 645.4861 |  | 516.3889 |  | SQ.M. | 22 | 11 | 8.8 | [6 empty] | SQ.M. | 22 | 11 | 8.8 | per hour | per
| 58.6806 |  | 35.2083 |  | 23.4722 |  | SQ.M. | 1 | 0.6 | 0.4 | [6 empty] | SQ.M. | 1 | 0.6 | 0.4 | per hour | per
| 0 |  | 0 |  | 0
| 126.1632 |  | 63.375 |  | 50.4653 |  | SQ.M. | 2.15 | 1.08 | 0.86 | [6 empty] | SQ.M. | 2.15 | 1.08 | 0.86 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 29.3403 |  | 14.6701 |  | 11.7361 |  | SQ.M. | 0.5 | 0.25 | 0.2 | [6 empty] | SQ.M. | 0.5 | 0.25 | 0.2 | per hour | per
| 151.3958 |  | 75.6979 |  | 60.441 |  | SQ.M. | 2.58 | 1.29 | 1.03 | [6 empty] | SQ.M. | 2.58 | 1.29 | 1.03 | per hour | per
| 120.8819 |  | 60.441 |  | 48.1181 |  | SQ.M. | 2.06 | 1.03 | 0.82 | [6 empty] | SQ.M. | 2.06 | 1.03 | 0.82 | per hour | per
| 99.7569 |  | 49.8785 |  | 39.9028 |  | SQ.M. | 1.7 | 0.85 | 0.68 | [6 empty] | SQ.M. | 1.7 | 0.85 | 0.68 | per hour | per
| 0 |  | 0 |  | 0 |  | SQ.M. | [9 empty] | SQ.M. |  |  |  | per hour | per
| 97.9965 |  | 48.7049 |  | 39.316 |  | SQ.M. | 1.67 | 0.83 | 0.67 | [6 empty] | SQ.M. | 1.67 | 0.83 | 0.67 | per hour | per
| 126.75 |  | 63.375 |  | 50.4653 |  | SQ.M. | 2.16 | 1.08 | 0.86 | [6 empty] | SQ.M. | 2.16 | 1.08 | 0.86 | per hour | per
| 0 |  | 0 |  | 0 |  | SQ.M. | [9 empty] | SQ.M. |  |  |  | per hour | per
| 410.7639 |  | 205.3819 |  | 164.3056 |  | SQ.M. | 7 | 3.5 | 2.8 | [6 empty] | SQ.M. | 7 | 3.5 | 2.8 | per hour | per
| 328.6111 |  | 164.3056 |  | 131.4444 |  | SQ.M. | 5.6 | 2.8 | 2.24 | [6 empty] | SQ.M. | 5.6 | 2.8 | 2.24 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 117.3611 |  | 58.6806 |  | 46.9444 |  | PC | 2 | 1 | 0.8 | [6 empty] | PC | 2 | 1 | 0.8 | per hour | per
| 17.0174 |  | 8.2153 |  | 6.4549 |  | B.F. | 0.29 | 0.14 | 0.11 | [6 empty] | B.F. | 0.29 | 0.14 | 0.11 | per hour | per
| 17.6042 |  | 21.125 |  | 17.0174 |  | B.F. | 0.3 | 0.36 | 0.29 | [6 empty] | B.F. | 0.3 | 0.36 | 0.29 | per hour | per
| 31.1007 |  | 15.8438 |  | 12.3229 |  | B.F. | 0.53 | 0.27 | 0.21 | [6 empty] | B.F. | 0.53 | 0.27 | 0.21 | per hour | per
| 113.8403 |  | 56.9201 |  | 45.184 |  | B.F. | 1.94 | 0.97 | 0.77 | [6 empty] | B.F. | 1.94 | 0.97 | 0.77 | per hour | per
| 49.8785 |  | 25.2326 |  | 19.9514 |  | B.F. | 0.85 | 0.43 | 0.34 | [6 empty] | B.F. | 0.85 | 0.43 | 0.34 | per hour | per
| 41.0764 |  | 20.5382 |  | 16.4306 |  | B.F. | 0.7 | 0.35 | 0.28 | [6 empty] | B.F. | 0.7 | 0.35 | 0.28 | per hour | per
| 93.8889 |  | 46.9444 |  | 37.5556 |  | B.F. | 1.6 | 0.8 | 0.64 | [6 empty] | B.F. | 1.6 | 0.8 | 0.64 | per hour | per
| 25.2326 |  | 12.3229 |  | 9.9757 |  | B.F. | 0.43 | 0.21 | 0.17 | [6 empty] | B.F. | 0.43 | 0.21 | 0.17 | per hour | per
| 15.8438 |  | 7.6285 |  | 6.4549 |  | B.F. | 0.27 | 0.13 | 0.11 | [6 empty] | B.F. | 0.27 | 0.13 | 0.11 | per hour | per
| 31.1007 |  | 15.8438 |  | 5.8681 |  | B.F. | 0.53 | 0.27 | 0.1 | [6 empty] | B.F. | 0.53 | 0.27 | 0.1 | per hour | per
| 53.3993 |  | 26.9931 |  | 21.125 |  | B.F. | 0.91 | 0.46 | 0.36 | [6 empty] | B.F. | 0.91 | 0.46 | 0.36 | per hour | per
| 0 |  | 0 |  | 0
| 117.3611 |  | 58.6806 |  | 46.9444 |  | PC | 2 | 1 | 0.8 | [6 empty] | PC | 2 | 1 | 0.8 | per hour | per
| 48.7049 |  | 24.6458 |  | 19.3646 |  | S.F. | 0.83 | 0.42 | 0.33 | [6 empty] | S.F. | 0.83 | 0.42 | 0.33 | per hour | per
| 0 |  | 0 |  | 0
| 156.0903 |  | 78.0451 |  | 62.2014 |  | SQ.M. | 2.66 | 1.33 | 1.06 | [6 empty] | SQ.M. | 2.66 | 1.33 | 1.06 | per hour | per
| 117.3611 |  | 58.6806 |  | 52.8125 |  | SQ.M. | 2 | 1 | 0.9 | [6 empty] | SQ.M. | 2 | 1 | 0.9 | per hour | per
| 15.2569 |  | 7.6285 |  | 5.8681 |  | B.F. | 0.26 | 0.13 | 0.1 | [6 empty] | B.F. | 0.26 | 0.13 | 0.1 | per hour | per
| 21.125 |  | 10.5625 |  | 8.2153 |  | B.F. | 0.36 | 0.18 | 0.14 | [6 empty] | B.F. | 0.36 | 0.18 | 0.14 | per hour | per
| 58.6806 |  | 29.3403 |  | 23.4722 |  | SQ.M. | 1 | 0.5 | 0.4 | [6 empty] | SQ.M. | 1 | 0.5 | 0.4 | per hour | per
| 821.5278 |  | 410.7639 |  | 328.6111 |  | SQ.M. | 14 | 7 | 5.6 | [6 empty] | SQ.M. | 14 | 7 | 5.6 | per hour | per
| 528.125 |  | 264.0625 |  | 211.25 |  | SQ.M. | 9 | 4.5 | 3.6 | [6 empty] | SQ.M. | 9 | 4.5 | 3.6 | per hour | per
| 410.7639 |  | 205.3819 |  | 164.3056 |  | SQ.M. | 7 | 3.5 | 2.8 | [6 empty] | SQ.M. | 7 | 3.5 | 2.8 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 46.9444 |  | 23.4722 |  | 18.7778 |  | PC. | 0.8 | 0.4 | 0.32 | [6 empty] | PC. | 0.8 | 0.4 | 0.32 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | PC. | 4 | 2 | 1.6 | [6 empty] | PC. | 4 | 2 | 1.6 | per hour | per
| 0 |  | 0 |  | 0
| 543.3819 |  | 271.691 |  | 217.1181 |  | SQ.M. | 9.26 | 4.63 | 3.7 | [6 empty] | SQ.M. | 9.26 | 4.63 | 3.7 | per hour | per
| 366.1667 |  | 183.0833 |  | 146.7014 |  | SQ.M. | 6.24 | 3.12 | 2.5 | [6 empty] | SQ.M. | 6.24 | 3.12 | 2.5 | per hour | per
| 543.3819 |  | 271.691 |  | 217.1181 |  | SQ.M. | 9.26 | 4.63 | 3.7 | [6 empty] | SQ.M. | 9.26 | 4.63 | 3.7 | per hour | per
| 372.0347 |  | 183.0833 |  | 146.7014 |  | SQ.M. | 6.34 | 3.12 | 2.5 | [6 empty] | SQ.M. | 6.34 | 3.12 | 2.5 | per hour | per
| 396.6806 |  | 198.3403 |  | 158.4375 |  | SQ.M. | 6.76 | 3.38 | 2.7 | [6 empty] | SQ.M. | 6.76 | 3.38 | 2.7 | per hour | per
| 1173.6111 |  | 586.8056 |  | 469.4444 |  | EACH | 20 | 10 | 8 | [6 empty] | EACH | 20 | 10 | 8 | per hour | per
| 1408.3333 |  | 704.1667 |  | 563.3333 |  | EACH | 24 | 12 | 9.6 | [6 empty] | EACH | 24 | 12 | 9.6 | per hour | per
| 1173.6111 |  | 586.8056 |  | 469.4444 |  | EACH | 20 | 10 | 8 | [6 empty] | EACH | 20 | 10 | 8 | per hour | per
| 2934.0278 |  | 1467.0139 |  | 1173.6111 |  | EACH | 50 | 25 | 20 | [6 empty] | EACH | 50 | 25 | 20 | per hour | per
| 36.9688 |  | 18.191 |  | 14.6701 |  | S.F. | 0.63 | 0.31 | 0.25 | [6 empty] | S.F. | 0.63 | 0.31 | 0.25 | per hour | per
| 187.7778 |  | 93.8889 |  | 75.1111 |  | SET | 3.2 | 1.6 | 1.28 | [6 empty] | SET | 3.2 | 1.6 | 1.28 | per hour | per
| 25.8194 |  | 12.9097 |  | 10.5625 |  | B.F. | 0.44 | 0.22 | 0.18 | [6 empty] | B.F. | 0.44 | 0.22 | 0.18 | per hour | per
| 38.7292 |  | 19.3646 |  | 15.2569 |  | B.F. | 0.66 | 0.33 | 0.26 | [6 empty] | B.F. | 0.66 | 0.33 | 0.26 | per hour | per
| 366.1667 |  | 183.0833 |  | 146.7014 |  | SQ.M. | 6.24 | 3.12 | 2.5 | [6 empty] | SQ.M. | 6.24 | 3.12 | 2.5 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 195.9931 |  | 97.9965 |  | 78.6319 |  | SQ.M. | 3.34 | 1.67 | 1.34 | [6 empty] | SQ.M. | 3.34 | 1.67 | 1.34 | per hour | per
| 167.8264 |  | 83.9132 |  | 78.6319 |  | SQ.M. | 2.86 | 1.43 | 1.34 | [6 empty] | SQ.M. | 2.86 | 1.43 | 1.34 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | SQ.M. | 4 | 2 | 1.6 | [6 empty] | SQ.M. | 4 | 2 | 1.6 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | SQ.M. | 10 | 5 | 4 | [6 empty] | SQ.M. | 10 | 5 | 4 | per hour | per
| 1235.8125 |  | 617.9062 |  | 494.0903 |  | SQ.M. | 21.06 | 10.53 | 8.42 | [6 empty] | SQ.M. | 21.06 | 10.53 | 8.42 | per hour | per
| 510.5208 |  | 255.2604 |  | 204.2083 |  | SQ.M. | 8.7 | 4.35 | 3.48 | [6 empty] | SQ.M. | 8.7 | 4.35 | 3.48 | per hour | per
| 352.0833 |  | 176.0417 |  | 140.8333 |  | SQ.M. | 6 | 3 | 2.4 | [6 empty] | SQ.M. | 6 | 3 | 2.4 | per hour | per
| 528.125 |  | 264.0625 |  | 211.25 |  | SQ.M. | 9 | 4.5 | 3.6 | [6 empty] | SQ.M. | 9 | 4.5 | 3.6 | per hour | per
| 469.4444 |  | 234.7222 |  | 187.7778 |  | SQ.M. | 8 | 4 | 3.2 | [6 empty] | SQ.M. | 8 | 4 | 3.2 | per hour | per
| 58.6806 |  | 29.3403 |  | 23.4722 |  | SQ.M. | 1 | 0.5 | 0.4 | [6 empty] | SQ.M. | 1 | 0.5 | 0.4 | per hour | per
| 352.0833 |  | 176.0417 |  | 199.5139 |  | SQ.M. | 6 | 3 | 3.4 | [6 empty] | SQ.M. | 6 | 3 | 3.4 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | SQ.M. | 4 | 2 | 1.6 | [6 empty] | SQ.M. | 4 | 2 | 1.6 | per hour | per
| 140.8333 |  | 70.4167 |  | 56.3333 |  | SQ.M. | 2.4 | 1.2 | 0.96 | [6 empty] | SQ.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 211.25 |  | 105.625 |  | 84.5 |  | SQ.M. | 3.6 | 1.8 | 1.44 | [6 empty] | SQ.M. | 3.6 | 1.8 | 1.44 | per hour | per
| 997.5694 |  | 557.4653 |  | 399.0278 |  | SQ.M. | 17 | 9.5 | 6.8 | [6 empty] | SQ.M. | 17 | 9.5 | 6.8 | per hour | per
| 133.7917 |  | 66.8958 |  | 53.3993 |  | SQ.M. | 2.28 | 1.14 | 0.91 | [6 empty] | SQ.M. | 2.28 | 1.14 | 0.91 | per hour | per
| 83.9132 |  | 42.25 |  | 33.4479 |  | SQ.M. | 1.43 | 0.72 | 0.57 | [6 empty] | SQ.M. | 1.43 | 0.72 | 0.57 | per hour | per
| 0 |  | 0 |  | 0
| 187.7778 |  | 93.8889 |  | 75.1111 |  | SQ.M. | 3.2 | 1.6 | 1.28 | [6 empty] | SQ.M. | 3.2 | 1.6 | 1.28 | per hour | per
| 156.0903 |  | 78.0451 |  | 62.2014 |  | SQ.M. | 2.66 | 1.33 | 1.06 | [6 empty] | SQ.M. | 2.66 | 1.33 | 1.06 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | SQ.M. | 4 | 2 | 1.6 | [6 empty] | SQ.M. | 4 | 2 | 1.6 | per hour | per
| 625.5347 |  | 312.7674 |  | 249.9792 |  | SQ.M. | 10.66 | 5.33 | 4.26 | [6 empty] | SQ.M. | 10.66 | 5.33 | 4.26 | per hour | per
| 700.6458 |  | 350.3229 |  | 280.4931 |  | SQ.M. | 11.94 | 5.97 | 4.78 | [6 empty] | SQ.M. | 11.94 | 5.97 | 4.78 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 126.75 |  | 63.375 |  | 50.4653 |  | SQ.M. | 2.16 | 1.08 | 0.86 | [6 empty] | SQ.M. | 2.16 | 1.08 | 0.86 | per hour | per
| 359.125 |  | 179.5625 |  | 143.7674 |  | SQ.M. | 6.12 | 3.06 | 2.45 | [6 empty] | SQ.M. | 6.12 | 3.06 | 2.45 | per hour | per
| 117.3611 |  | 58.6806 |  | 46.9444 |  | SHT. | 2 | 1 | 0.8 | [6 empty] | SHT. | 2 | 1 | 0.8 | per hour | per
| 93.8889 |  | 575.0694 |  | 37.5556 |  | SHT. | 1.6 | 9.8 | 0.64 | [6 empty] | SHT. | 1.6 | 9.8 | 0.64 | per hour | per
| 59.2674 |  | 29.9271 |  | 23.4722 |  | L.M. | 1.01 | 0.51 | 0.4 | [6 empty] | L.M. | 1.01 | 0.51 | 0.4 | per hour | per
| 407.2431 |  | 203.6215 |  | 163.1319 |  | SHT. | 6.94 | 3.47 | 2.78 | [6 empty] | SHT. | 6.94 | 3.47 | 2.78 | per hour | per
| 96.2361 |  | 48.1181 |  | 38.7292 |  | SHT. | 1.64 | 0.82 | 0.66 | [6 empty] | SHT. | 1.64 | 0.82 | 0.66 | per hour | per
| 61.6146 |  | 31.1007 |  | 24.6458 |  | L.M. | 1.05 | 0.53 | 0.42 | [6 empty] | L.M. | 1.05 | 0.53 | 0.42 | per hour | per
| 113.8403 |  | 56.9201 |  | 104.4514 |  | L.M. | 1.94 | 0.97 | 1.78 | [6 empty] | L.M. | 1.94 | 0.97 | 1.78 | per hour | per
| 18.7778 |  | 9.3889 |  | 7.6285 |  | L.M. | 0.32 | 0.16 | 0.13 | [6 empty] | L.M. | 0.32 | 0.16 | 0.13 | per hour | per
| 104.4514 |  | 528.125 |  | 41.6632 |  | L.M. | 1.78 | 9 | 0.71 | [6 empty] | L.M. | 1.78 | 9 | 0.71 | per hour | per
| 34.6215 |  | 17.6042 |  | 14.0833 |  | L.M. | 0.59 | 0.3 | 0.24 | [6 empty] | L.M. | 0.59 | 0.3 | 0.24 | per hour | per
| 15.8438 |  | 7.6285 |  | 6.4549 |  | L.M. | 0.27 | 0.13 | 0.11 | [6 empty] | L.M. | 0.27 | 0.13 | 0.11 | per hour | per
| 211.25 |  | 105.625 |  | 84.5 |  | SQ.M. | 3.6 | 1.8 | 1.44 | [6 empty] | SQ.M. | 3.6 | 1.8 | 1.44 | per hour | per
| 211.25 |  | 105.625 |  | 84.5 |  | SQ.M. | 3.6 | 1.8 | 1.44 | [6 empty] | SQ.M. | 3.6 | 1.8 | 1.44 | per hour | per
| 997.5694 |  | 498.7847 |  | 399.0278 |  | SQ.M. | 17 | 8.5 | 6.8 | [6 empty] | SQ.M. | 17 | 8.5 | 6.8 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | SQ.M. | 4 | 2 | 1.6 | [6 empty] | SQ.M. | 4 | 2 | 1.6 | per hour | per
| 199.5139 |  | 99.7569 |  | 79.8056 |  | SQ.M. | 3.4 | 1.7 | 1.36 | [6 empty] | SQ.M. | 3.4 | 1.7 | 1.36 | per hour | per
| 70.4167 |  | 35.2083 |  | 28.1667 |  | SQ.M. | 1.2 | 0.6 | 0.48 | [6 empty] | SQ.M. | 1.2 | 0.6 | 0.48 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 586.8056 |  | 293.4028 |  | 234.7222 |  | CU.M. | 10 | 5 | 4 | [6 empty] | CU.M. | 10 | 5 | 4 | per hour | per
| 2934.0278 |  | 1467.0139 |  | 1173.6111 |  | CU.M. | 50 | 25 | 20 | [6 empty] | CU.M. | 50 | 25 | 20 | per hour | per
| 117.3611 |  | 58.6806 |  | 46.9444 |  | SQ.M. | 2 | 1 | 0.8 | [6 empty] | SQ.M. | 2 | 1 | 0.8 | per hour | per
| 167.8264 |  | 83.9132 |  | 66.8958 |  | SQ.M. | 2.86 | 1.43 | 1.14 | [6 empty] | SQ.M. | 2.86 | 1.43 | 1.14 | per hour | per
| 0 |  | 0 |  | 0
| 8.2153 |  | 4.1076 |  | 3.5208 |  | KGS | 0.14 | 0.07 | 0.06 | [6 empty] | KGS | 0.14 | 0.07 | 0.06 | per hour | per
| 9.3889 |  | 4.6944 |  | 3.5208 |  | KGS | 0.16 | 0.08 | 0.06 | [6 empty] | KGS | 0.16 | 0.08 | 0.06 | per hour | per
| 11.7361 |  | 5.8681 |  | 4.6944 |  | KGS | 0.2 | 0.1 | 0.08 | [6 empty] | KGS | 0.2 | 0.1 | 0.08 | per hour | per
| 1877.7778 |  | 938.8889 |  | 751.1111 |  | CU.M. | 32 | 16 | 12.8 | [6 empty] | CU.M. | 32 | 16 | 12.8 | per hour | per
| 211.25 |  | 105.625 |  | 84.5 |  | CU.M. | 3.6 | 1.8 | 1.44 | [6 empty] | CU.M. | 3.6 | 1.8 | 1.44 | per hour | per
| 0 |  | 0 |  | 0
| 821.5278 |  | 410.7639 |  | 328.6111 |  | CU.M. | 14 | 7 | 5.6 | [6 empty] | CU.M. | 14 | 7 | 5.6 | per hour | per
| 1643.0556 |  | 821.5278 |  | 657.2222 |  | CU.M. | 28 | 14 | 11.2 | [6 empty] | CU.M. | 28 | 14 | 11.2 | per hour | per
| 3168.75 |  | 1584.375 |  | 1267.5 |  | CU.M. | 54 | 27 | 21.6 | [6 empty] | CU.M. | 54 | 27 | 21.6 | per hour | per
| 328.6111 |  | 164.3056 |  | 131.4444 |  | SQ.M. | 5.6 | 2.8 | 2.24 | [6 empty] | SQ.M. | 5.6 | 2.8 | 2.24 | per hour | per
| 0 |  | 0 |  | 0
| 2464.5833 |  | 1232.2917 |  | 985.8333 |  | CU.M. | 42 | 21 | 16.8 | [6 empty] | CU.M. | 42 | 21 | 16.8 | per hour | per
| 62.2014 |  | 31.1007 |  | 24.6458 |  | KGS | 1.06 | 0.53 | 0.42 | [6 empty] | KGS | 1.06 | 0.53 | 0.42 | per hour | per
| 38.7292 |  | 19.3646 |  | 15.2569 |  | KGS | 0.66 | 0.33 | 0.26 | [6 empty] | KGS | 0.66 | 0.33 | 0.26 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 70.4167 |  | 35.2083 |  | 28.1667 |  | CU.M. | 1.2 | 0.6 | 0.48 | [6 empty] | CU.M. | 1.2 | 0.6 | 0.48 | per hour | per
| 93.8889 |  | 46.9444 |  | 37.5556 |  | CU.M. | 1.6 | 0.8 | 0.64 | [6 empty] | CU.M. | 1.6 | 0.8 | 0.64 | per hour | per
| 129.0972 |  | 64.5486 |  | 51.6389 |  | CU.M. | 2.2 | 1.1 | 0.88 | [6 empty] | CU.M. | 2.2 | 1.1 | 0.88 | per hour | per
| 140.8333 |  | 70.4167 |  | 56.3333 |  | CU.M. | 2.4 | 1.2 | 0.96 | [6 empty] | CU.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 176.0417 |  | 88.0208 |  | 70.4167 |  | CU.M. | 3 | 1.5 | 1.2 | [6 empty] | CU.M. | 3 | 1.5 | 1.2 | per hour | per
| 0 |  | 0 |  | 0
| 469.4444 |  | 234.7222 |  | 187.7778 |  | CU.M. | 8 | 4 | 3.2 | [6 empty] | CU.M. | 8 | 4 | 3.2 | per hour | per
| 762.8472 |  | 381.4236 |  | 305.1389 |  | CU.M. | 13 | 6.5 | 5.2 | [6 empty] | CU.M. | 13 | 6.5 | 5.2 | per hour | per
| 1232.2917 |  | 616.1458 |  | 492.9167 |  | CU.M. | 21 | 10.5 | 8.4 | [6 empty] | CU.M. | 21 | 10.5 | 8.4 | per hour | per
| 645.4861 |  | 322.7431 |  | 258.1944 |  | CU.M. | 11 | 5.5 | 4.4 | [6 empty] | CU.M. | 11 | 5.5 | 4.4 | per hour | per
| 938.8889 |  | 469.4444 |  | 375.5556 |  | CU.M. | 16 | 8 | 6.4 | [6 empty] | CU.M. | 16 | 8 | 6.4 | per hour | per
| 1408.3333 |  | 704.1667 |  | 563.3333 |  | CU.M. | 24 | 12 | 9.6 | [6 empty] | CU.M. | 24 | 12 | 9.6 | per hour | per
| 0 |  | 0 |  | 0
| 152.5694 |  | 76.2847 |  | 61.0278 |  | SQ.M. | 2.6 | 1.3 | 1.04 | [6 empty] | SQ.M. | 2.6 | 1.3 | 1.04 | per hour | per
| 2112.5 |  | 1056.25 |  | 845 |  | CU.M. | 36 | 18 | 14.4 | [6 empty] | CU.M. | 36 | 18 | 14.4 | per hour | per
| 0 |  | 0 |  | 0
| 52.8125 |  | 26.4062 |  | 21.125 |  | SQ.M. | 0.9 | 0.45 | 0.36 | [6 empty] | SQ.M. | 0.9 | 0.45 | 0.36 | per hour | per
| 64.5486 |  | 32.2743 |  | 25.8194 |  | SQ.M. | 1.1 | 0.55 | 0.44 | [6 empty] | SQ.M. | 1.1 | 0.55 | 0.44 | per hour | per
| 140.8333 |  | 70.4167 |  | 56.3333 |  | CU.M. | 2.4 | 1.2 | 0.96 | [6 empty] | CU.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 0 |  | 0 |  | 0
| 14.0833 |  | 7.0417 |  | 5.8681 |  | SQ.M. | 0.24 | 0.12 | 0.1 | [6 empty] | SQ.M. | 0.24 | 0.12 | 0.1 | per hour | per
| 211.25 |  | 105.625 |  | 84.5 |  | CU.M. | 3.6 | 1.8 | 1.44 | [6 empty] | CU.M. | 3.6 | 1.8 | 1.44 | per hour | per
| 152.5694 |  | 76.2847 |  | 61.0278 |  | SQ.M. | 2.6 | 1.3 | 1.04 | [6 empty] | SQ.M. | 2.6 | 1.3 | 1.04 | per hour | per
| 164.3056 |  | 82.1528 |  | 65.7222 |  | SQ.M. | 2.8 | 1.4 | 1.12 | [6 empty] | SQ.M. | 2.8 | 1.4 | 1.12 | per hour | per
| 176.0417 |  | 88.0208 |  | 70.4167 |  | SQ.M. | 3 | 1.5 | 1.2 | [6 empty] | SQ.M. | 3 | 1.5 | 1.2 | per hour | per
| 37.5556 |  | 18.7778 |  | 15.2569 |  | SQ.M. | 0.64 | 0.32 | 0.26 | [6 empty] | SQ.M. | 0.64 | 0.32 | 0.26 | per hour | per
| 140.8333 |  | 70.4167 |  | 56.3333 |  | SQ.M. | 2.4 | 1.2 | 0.96 | [6 empty] | SQ.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 37.5556 |  | 18.7778 |  | 15.2569 |  | SQ.M. | 0.64 | 0.32 | 0.26 | [6 empty] | SQ.M. | 0.64 | 0.32 | 0.26 | per hour | per
| 49.2917 |  | 24.6458 |  | 19.9514 |  | SQ.M. | 0.84 | 0.42 | 0.34 | [6 empty] | SQ.M. | 0.84 | 0.42 | 0.34 | per hour | per
| 61.0278 |  | 30.5139 |  | 24.6458 |  | SQ.M. | 1.04 | 0.52 | 0.42 | [6 empty] | SQ.M. | 1.04 | 0.52 | 0.42 | per hour | per
| 70.4167 |  | 35.2083 |  | 28.1667 |  | CU.M. | 1.2 | 0.6 | 0.48 | [6 empty] | CU.M. | 1.2 | 0.6 | 0.48 | per hour | per
| 0 |  | 0 |  | 0
| 49.2917 |  | 24.6458 |  | 19.9514 |  | SQ.M. | 0.84 | 0.42 | 0.34 | [6 empty] | SQ.M. | 0.84 | 0.42 | 0.34 | per hour | per
| 23.4722 |  | 11.7361 |  | 9.3889 |  | SQ.M. | 0.4 | 0.2 | 0.16 | [6 empty] | SQ.M. | 0.4 | 0.2 | 0.16 | per hour | per
| 23.4722 |  | 11.7361 |  | 9.3889 |  | SQ.M. | 0.4 | 0.2 | 0.16 | [6 empty] | SQ.M. | 0.4 | 0.2 | 0.16 | per hour | per
| 0 |  | 0 |  | 0
| 49.2917 |  | 24.6458 |  | 19.9514 |  | SQ.M. | 0.84 | 0.42 | 0.34 | [6 empty] | SQ.M. | 0.84 | 0.42 | 0.34 | per hour | per
| 492.9167 |  | 246.4583 |  | 197.1667 |  | SQ.M. | 8.4 | 4.2 | 3.36 | [6 empty] | SQ.M. | 8.4 | 4.2 | 3.36 | per hour | per
| 0 |  | 0 |  | 0
| 37.5556 |  | 18.7778 |  | 15.2569 |  | SQ.M. | 0.64 | 0.32 | 0.26 | [6 empty] | SQ.M. | 0.64 | 0.32 | 0.26 | per hour | per
| 49.2917 |  | 24.6458 |  | 19.9514 |  | SQ.M. | 0.84 | 0.42 | 0.34 | [6 empty] | SQ.M. | 0.84 | 0.42 | 0.34 | per hour | per
| 61.0278 |  | 30.5139 |  | 24.6458 |  | SQ.M. | 1.04 | 0.52 | 0.42 | [6 empty] | SQ.M. | 1.04 | 0.52 | 0.42 | per hour | per
| 0 |  | 0 |  | 0
| 82.1528 |  | 41.0764 |  | 32.8611 |  | CU.M. | 1.4 | 0.7 | 0.56 | [6 empty] | CU.M. | 1.4 | 0.7 | 0.56 | per hour | per
| 23.4722 |  | 11.7361 |  | 9.3889 |  | SQ.M. | 0.4 | 0.2 | 0.16 | [6 empty] | SQ.M. | 0.4 | 0.2 | 0.16 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | CU.M. | 4 | 2 | 1.6 | [6 empty] | CU.M. | 4 | 2 | 1.6 | per hour | per
| 0 |  | 0 |  | 0
| 938.8889 |  | 469.4444 |  | 375.5556 |  | CU.M. | 16 | 8 | 6.4 | [6 empty] | CU.M. | 16 | 8 | 6.4 | per hour | per
| 153.7431 |  | 76.8715 |  | 61.6146 |  | CU.M. | 2.62 | 1.31 | 1.05 | [6 empty] | CU.M. | 2.62 | 1.31 | 1.05 | per hour | per
| 192.4722 |  | 96.2361 |  | 76.8715 |  | CU.M. | 3.28 | 1.64 | 1.31 | [6 empty] | CU.M. | 3.28 | 1.64 | 1.31 | per hour | per
| 308.6597 |  | 154.3299 |  | 123.2292 |  | CU.M. | 5.26 | 2.63 | 2.1 | [6 empty] | CU.M. | 5.26 | 2.63 | 2.1 | per hour | per
| 0 |  | 0 |  | 0
| 782.7986 |  | 391.3993 |  | 313.3542 |  | CU.M. | 13.34 | 6.67 | 5.34 | [6 empty] | CU.M. | 13.34 | 6.67 | 5.34 | per hour | per
| 1956.4097 |  | 978.2049 |  | 782.7986 |  | CU.M. | 33.34 | 16.67 | 13.34 | [6 empty] | CU.M. | 33.34 | 16.67 | 13.34 | per hour | per
| 0 |  | 0 |  | 0
| 96.2361 |  | 48.1181 |  | 38.7292 |  | CU.M. | 1.64 | 0.82 | 0.66 | [6 empty] | CU.M. | 1.64 | 0.82 | 0.66 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | CU.M. | 10 | 5 | 4 | [6 empty] | CU.M. | 10 | 5 | 4 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 146.7014 |  | 73.3507 |  | 58.6806 |  | L.M. | 2.5 | 1.25 | 1 | [6 empty] | L.M. | 2.5 | 1.25 | 1 | per hour | per
| 195.9931 |  | 97.9965 |  | 137.3125 |  | L.M. | 3.34 | 1.67 | 2.34 | [6 empty] | L.M. | 3.34 | 1.67 | 2.34 | per hour | per
| 293.4028 |  | 146.7014 |  | 117.3611 |  | L.M. | 5 | 2.5 | 2 | [6 empty] | L.M. | 5 | 2.5 | 2 | per hour | per
| 390.8125 |  | 195.4062 |  | 156.0903 |  | L.M. | 6.66 | 3.33 | 2.66 | [6 empty] | L.M. | 6.66 | 3.33 | 2.66 | per hour | per
| 12.3229 |  | 6.4549 |  | 4.6944 |  | CU.M. | 0.21 | 0.11 | 0.08 | [6 empty] | CU.M. | 0.21 | 0.11 | 0.08 | per hour | per
| 24.6458 |  | 12.3229 |  | 9.9757 |  | CU.M. | 0.42 | 0.21 | 0.17 | [6 empty] | CU.M. | 0.42 | 0.21 | 0.17 | per hour | per
| 56.3333 |  | 28.1667 |  | 22.2986 |  | SQ.M. | 0.96 | 0.48 | 0.38 | [6 empty] | SQ.M. | 0.96 | 0.48 | 0.38 | per hour | per
| 6.4549 |  | 3.5208 |  | 2.3472 |  | CU.M. | 0.11 | 0.06 | 0.04 | [6 empty] | CU.M. | 0.11 | 0.06 | 0.04 | per hour | per
| 0 |  | 0 |  | 0
| 5.8681 |  | 2.934 |  | 2.3472 |  | SQ.M. | 0.1 | 0.05 | 0.04 | [6 empty] | SQ.M. | 0.1 | 0.05 | 0.04 | per hour | per
| 3.5208 |  | 1.7604 |  | 1.1736 |  | SQ.M. | 0.06 | 0.03 | 0.02 | [6 empty] | SQ.M. | 0.06 | 0.03 | 0.02 | per hour | per
| 198.3403 |  | 99.1701 |  | 79.2188 |  | CU.M. | 3.38 | 1.69 | 1.35 | [6 empty] | CU.M. | 3.38 | 1.69 | 1.35 | per hour | per
| 117.3611 |  | 58.6806 |  | 46.9444 |  | CU.M. | 2 | 1 | 0.8 | [6 empty] | CU.M. | 2 | 1 | 0.8 | per hour | per
| 242.9375 |  | 121.4688 |  | 97.4097 |  | CU.M. | 4.14 | 2.07 | 1.66 | [6 empty] | CU.M. | 4.14 | 2.07 | 1.66 | per hour | per
| 0 |  | 0 |  | 0
| 125.5764 |  | 62.7882 |  | 50.4653 |  | CU.M. | 2.14 | 1.07 | 0.86 | [6 empty] | CU.M. | 2.14 | 1.07 | 0.86 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 77.4583 |  | 38.7292 |  | 31.1007 |  | L.M. | 1.32 | 0.66 | 0.53 | [6 empty] | L.M. | 1.32 | 0.66 | 0.53 | per hour | per
| 77.4583 |  | 38.7292 |  | 31.1007 |  | L.M. | 1.32 | 0.66 | 0.53 | [6 empty] | L.M. | 1.32 | 0.66 | 0.53 | per hour | per
| 86.8472 |  | 43.4236 |  | 34.6215 |  | L.M. | 1.48 | 0.74 | 0.59 | [6 empty] | L.M. | 1.48 | 0.74 | 0.59 | per hour | per
| 96.2361 |  | 48.1181 |  | 38.7292 |  | L.M. | 1.64 | 0.82 | 0.66 | [6 empty] | L.M. | 1.64 | 0.82 | 0.66 | per hour | per
| 115.6007 |  | 57.5069 |  | 41.0764 |  | L.M. | 1.97 | 0.98 | 0.7 | [6 empty] | L.M. | 1.97 | 0.98 | 0.7 | per hour | per
| 126.75 |  | 63.375 |  | 50.4653 |  | L.M. | 2.16 | 1.08 | 0.86 | [6 empty] | L.M. | 2.16 | 1.08 | 0.86 | per hour | per
| 134.9653 |  | 67.4826 |  | 53.9861 |  | L.M. | 2.3 | 1.15 | 0.92 | [6 empty] | L.M. | 2.3 | 1.15 | 0.92 | per hour | per
| 154.9167 |  | 77.4583 |  | 62.2014 |  | L.M. | 2.64 | 1.32 | 1.06 | [6 empty] | L.M. | 2.64 | 1.32 | 1.06 | per hour | per
| 0 |  | 0 |  | 0
| 257.0208 |  | 128.5104 |  | 102.691 |  | L.M. | 4.38 | 2.19 | 1.75 | [6 empty] | L.M. | 4.38 | 2.19 | 1.75 | per hour | per
| 386.1181 |  | 193.059 |  | 154.3299 |  | L.M. | 6.58 | 3.29 | 2.63 | [6 empty] | L.M. | 6.58 | 3.29 | 2.63 | per hour | per
| 577.4167 |  | 288.7083 |  | 231.2014 |  | L.M. | 9.84 | 4.92 | 3.94 | [6 empty] | L.M. | 9.84 | 4.92 | 3.94 | per hour | per
| 771.0625 |  | 385.5312 |  | 308.6597 |  | L.M. | 13.14 | 6.57 | 5.26 | [6 empty] | L.M. | 13.14 | 6.57 | 5.26 | per hour | per
| 1156.0069 |  | 578.0035 |  | 468.2708 |  | L.M. | 19.7 | 9.85 | 7.98 | [6 empty] | L.M. | 19.7 | 9.85 | 7.98 | per hour | per
| 1209.9931 |  | 604.9965 |  | 484.1146 |  | L.M. | 20.62 | 10.31 | 8.25 | [6 empty] | L.M. | 20.62 | 10.31 | 8.25 | per hour | per
| 1414.2014 |  | 707.1007 |  | 565.6806 |  | L.M. | 24.1 | 12.05 | 9.64 | [6 empty] | L.M. | 24.1 | 12.05 | 9.64 | per hour | per
| 1606.6736 |  | 803.3368 |  | 642.5521 |  | L.M. | 27.38 | 13.69 | 10.95 | [6 empty] | L.M. | 27.38 | 13.69 | 10.95 | per hour | per
| 1800.3194 |  | 900.1597 |  | 720.0104 |  | L.M. | 30.68 | 15.34 | 12.27 | [6 empty] | L.M. | 30.68 | 15.34 | 12.27 | per hour | per
| 1928.2431 |  | 964.1215 |  | 771.0625 |  | L.M. | 32.86 | 16.43 | 13.14 | [6 empty] | L.M. | 32.86 | 16.43 | 13.14 | per hour | per
| 2120.7153 |  | 1060.3576 |  | 848.5208 |  | L.M. | 36.14 | 18.07 | 14.46 | [6 empty] | L.M. | 36.14 | 18.07 | 14.46 | per hour | per
| 2410.5972 |  | 1205.2986 |  | 964.1215 |  | L.M. | 41.08 | 20.54 | 16.43 | [6 empty] | L.M. | 41.08 | 20.54 | 16.43 | per hour | per
| 0 |  | 0 |  | 0
| 22.2986 |  | 11.1493 |  | 8.8021 |  | L.M. | 0.38 | 0.19 | 0.15 | [6 empty] | L.M. | 0.38 | 0.19 | 0.15 | per hour | per
| 86.8472 |  | 43.4236 |  | 34.6215 |  | L.M. | 1.48 | 0.74 | 0.59 | [6 empty] | L.M. | 1.48 | 0.74 | 0.59 | per hour | per
| 96.2361 |  | 48.1181 |  | 38.7292 |  | L.M. | 1.64 | 0.82 | 0.66 | [6 empty] | L.M. | 1.64 | 0.82 | 0.66 | per hour | per
| 115.0139 |  | 57.5069 |  | 45.7708 |  | L.M. | 1.96 | 0.98 | 0.78 | [6 empty] | L.M. | 1.96 | 0.98 | 0.78 | per hour | per
| 126.75 |  | 63.375 |  | 50.4653 |  | L.M. | 2.16 | 1.08 | 0.86 | [6 empty] | L.M. | 2.16 | 1.08 | 0.86 | per hour | per
| 153.7431 |  | 76.8715 |  | 61.6146 |  | L.M. | 2.62 | 1.31 | 1.05 | [6 empty] | L.M. | 2.62 | 1.31 | 1.05 | per hour | per
| 192.4722 |  | 96.2361 |  | 76.8715 |  | L.M. | 3.28 | 1.64 | 1.31 | [6 empty] | L.M. | 3.28 | 1.64 | 1.31 | per hour | per
| 288.7083 |  | 144.3542 |  | 115.6007 |  | L.M. | 4.92 | 2.46 | 1.97 | [6 empty] | L.M. | 4.92 | 2.46 | 1.97 | per hour | per
| 0 |  | 0 |  | 0
| 528.125 |  | 234.7222 |  | 187.7778 |  | L.M. | 9 | 4 | 3.2 | [6 empty] | L.M. | 9 | 4 | 3.2 | per hour | per
| 751.1111 |  | 375.5556 |  | 300.4444 |  | L.M. | 12.8 | 6.4 | 5.12 | [6 empty] | L.M. | 12.8 | 6.4 | 5.12 | per hour | per
| 1252.2431 |  | 626.1215 |  | 501.1319 |  | L.M. | 21.34 | 10.67 | 8.54 | [6 empty] | L.M. | 21.34 | 10.67 | 8.54 | per hour | per
| 156.0903 |  | 78.0451 |  | 62.2014 |  | L.M. | 2.66 | 1.33 | 1.06 | [6 empty] | L.M. | 2.66 | 1.33 | 1.06 | per hour | per
| 0 |  | 0 |  | 0
| 938.8889 |  | 469.4444 |  | 375.5556 |  | EACH | 16 | 8 | 6.4 | [6 empty] | EACH | 16 | 8 | 6.4 | per hour | per
| 1408.3333 |  | 704.1667 |  | 563.3333 |  | EACH | 24 | 12 | 9.6 | [6 empty] | EACH | 24 | 12 | 9.6 | per hour | per
| 2816.6667 |  | 1408.3333 |  | 1126.6667 |  | EACH | 48 | 24 | 19.2 | [6 empty] | EACH | 48 | 24 | 19.2 | per hour | per
| 1877.7778 |  | 938.8889 |  | 751.1111 |  | EACH | 32 | 16 | 12.8 | [6 empty] | EACH | 32 | 16 | 12.8 | per hour | per
| 1173.6111 |  | 586.8056 |  | 469.4444 |  | EACH | 20 | 10 | 8 | [6 empty] | EACH | 20 | 10 | 8 | per hour | per
| 4225 |  | 2112.5 |  | 1690 |  | EACH | 72 | 36 | 28.8 | [6 empty] | EACH | 72 | 36 | 28.8 | per hour | per
| 2816.6667 |  | 1408.3333 |  | 1126.6667 |  | EACH | 48 | 24 | 19.2 | [6 empty] | EACH | 48 | 24 | 19.2 | per hour | per
| 1643.0556 |  | 821.5278 |  | 657.2222 |  | EACH | 28 | 14 | 11.2 | [6 empty] | EACH | 28 | 14 | 11.2 | per hour | per
| 1643.0556 |  | 821.5278 |  | 657.2222 |  | EACH | 28 | 14 | 11.2 | [6 empty] | EACH | 28 | 14 | 11.2 | per hour | per
| 3051.3889 |  | 1525.6944 |  | 1220.5556 |  | EACH | 52 | 26 | 20.8 | [6 empty] | EACH | 52 | 26 | 20.8 | per hour | per
| 1525.6944 |  | 762.8472 |  | 610.2778 |  | EACH | 26 | 13 | 10.4 | [6 empty] | EACH | 26 | 13 | 10.4 | per hour | per
| 938.8889 |  | 528.125 |  | 375.5556 |  | EACH | 16 | 9 | 6.4 | [6 empty] | EACH | 16 | 9 | 6.4 | per hour | per
| 234.7222 |  | 117.3611 |  | 93.8889 |  | EACH | 4 | 2 | 1.6 | [6 empty] | EACH | 4 | 2 | 1.6 | per hour | per
| 938.8889 |  | 469.4444 |  | 375.5556 |  | EACH | 16 | 8 | 6.4 | [6 empty] | EACH | 16 | 8 | 6.4 | per hour | per
| 469.4444 |  | 234.7222 |  | 187.7778 |  | PIPE | 8 | 4 | 3.2 | [6 empty] | PIPE | 8 | 4 | 3.2 | per hour | per
| 751.1111 |  | 375.5556 |  | 300.4444 |  | PIPE | 12.8 | 6.4 | 5.12 | [6 empty] | PIPE | 12.8 | 6.4 | 5.12 | per hour | per
| 1251.0694 |  | 625.5347 |  | 500.5451 |  | PIPE | 21.32 | 10.66 | 8.53 | [6 empty] | PIPE | 21.32 | 10.66 | 8.53 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 293.4028 |  | 146.7014 |  | 117.3611 |  | S.M. | 5 | 2.5 | 2 | [6 empty] | S.M. | 5 | 2.5 | 2 | per hour | per
| 1408.3333 |  | 704.1667 |  | 563.3333 |  | S.M. | 24 | 12 | 9.6 | [6 empty] | S.M. | 24 | 12 | 9.6 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | S.M. | 10 | 5 | 4 | [6 empty] | S.M. | 10 | 5 | 4 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | S.M. | 10 | 5 | 4 | [6 empty] | S.M. | 10 | 5 | 4 | per hour | per
| 0 |  | 0 |  | 0
| 1995.1389 |  | 997.5694 |  | 798.0556 |  | S.M. | 34 | 17 | 13.6 | [6 empty] | S.M. | 34 | 17 | 13.6 | per hour | per
| 3520.8333 |  | 1760.4167 |  | 1408.3333 |  | S.M. | 60 | 30 | 24 | [6 empty] | S.M. | 60 | 30 | 24 | per hour | per
| 0 |  | 0 |  | 0
| 469.4444 |  | 234.7222 |  | 187.7778 |  | FLG. | 8 | 4 | 3.2 | [6 empty] | FLG. | 8 | 4 | 3.2 | per hour | per
| 93.8889 |  | 46.9444 |  | 37.5556 |  | S.M. | 1.6 | 0.8 | 0.64 | [6 empty] | S.M. | 1.6 | 0.8 | 0.64 | per hour | per
| 316.875 |  | 158.4375 |  | 126.75 |  | L.M. | 5.4 | 2.7 | 2.16 | [6 empty] | L.M. | 5.4 | 2.7 | 2.16 | per hour | per
| 176.0417 |  | 88.0208 |  | 70.4167 |  | EACH | 3 | 1.5 | 1.2 | [6 empty] | EACH | 3 | 1.5 | 1.2 | per hour | per
| 938.8889 |  | 469.4444 |  | 375.5556 |  | EACH | 16 | 8 | 6.4 | [6 empty] | EACH | 16 | 8 | 6.4 | per hour | per
| 704.1667 |  | 352.0833 |  | 281.6667 |  | EACH | 12 | 6 | 4.8 | [6 empty] | EACH | 12 | 6 | 4.8 | per hour | per
| 469.4444 |  | 234.7222 |  | 187.7778 |  | EACH | 8 | 4 | 3.2 | [6 empty] | EACH | 8 | 4 | 3.2 | per hour | per
| 434.2361 |  | 217.1181 |  | 173.6944 |  | L.M. | 7.4 | 3.7 | 2.96 | [6 empty] | L.M. | 7.4 | 3.7 | 2.96 | per hour | per
| 176.0417 |  | 88.0208 |  | 70.4167 |  | L.M. | 3 | 1.5 | 1.2 | [6 empty] | L.M. | 3 | 1.5 | 1.2 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 58.6806 |  | 29.3403 |  | 23.4722 |  | EACH | 1 | 0.5 | 0.4 | [6 empty] | EACH | 1 | 0.5 | 0.4 | per hour | per
| 140.8333 |  | 70.4167 |  | 56.3333 |  | S.M. | 2.4 | 1.2 | 0.96 | [6 empty] | S.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 0 |  | 0 |  | 0
| 1643.0556 |  | 821.5278 |  | 657.2222 |  | S.M. | 28 | 14 | 11.2 | [6 empty] | S.M. | 28 | 14 | 11.2 | per hour | per
| 704.1667 |  | 352.0833 |  | 281.6667 |  | S.M. | 12 | 6 | 4.8 | [6 empty] | S.M. | 12 | 6 | 4.8 | per hour | per
| 8215.2778 |  | 4107.6389 |  | 3286.1111 |  | S.M. | 140 | 70 | 56 | [6 empty] | S.M. | 140 | 70 | 56 | per hour | per
| 70.4167 |  | 35.2083 |  | 28.1667 |  | S.M. | 1.2 | 0.6 | 0.48 | [6 empty] | S.M. | 1.2 | 0.6 | 0.48 | per hour | per
| 82.1528 |  | 41.0764 |  | 32.8611 |  | S.M. | 1.4 | 0.7 | 0.56 | [6 empty] | S.M. | 1.4 | 0.7 | 0.56 | per hour | per
| 316.875 |  | 158.4375 |  | 126.75 |  | S.M. | 5.4 | 2.7 | 2.16 | [6 empty] | S.M. | 5.4 | 2.7 | 2.16 | per hour | per
| 0 |  | 0 |  | 0
| 140.8333 |  | 70.4167 |  | 56.3333 |  | S.M. | 2.4 | 1.2 | 0.96 | [6 empty] | S.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 93.8889 |  | 46.9444 |  | 37.5556 |  | PC. | 1.6 | 0.8 | 0.64 | [6 empty] | PC. | 1.6 | 0.8 | 0.64 | per hour | per
| 293.4028 |  | 146.7014 |  | 117.3611 |  | S.M. | 5 | 2.5 | 2 | [6 empty] | S.M. | 5 | 2.5 | 2 | per hour | per
| 352.0833 |  | 176.0417 |  | 140.8333 |  | S.M. | 6 | 3 | 2.4 | [6 empty] | S.M. | 6 | 3 | 2.4 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 586.8056 |  | 293.4028 |  | 234.7222 |  | EACH | 10 | 5 | 4 | [6 empty] | EACH | 10 | 5 | 4 | per hour | per
| 1760.4167 |  | 880.2083 |  | 704.1667 |  | EACH | 30 | 15 | 12 | [6 empty] | EACH | 30 | 15 | 12 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | EACH | 10 | 5 | 4 | [6 empty] | EACH | 10 | 5 | 4 | per hour | per
| 0 |  | 0 |  | 0
| 1173.6111 |  | 586.8056 |  | 469.4444 |  | EACH | 20 | 10 | 8 | [6 empty] | EACH | 20 | 10 | 8 | per hour | per
| 1173.6111 |  | 586.8056 |  | 469.4444 |  | EACH | 20 | 10 | 8 | [6 empty] | EACH | 20 | 10 | 8 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | EACH | 10 | 5 | 4 | [6 empty] | EACH | 10 | 5 | 4 | per hour | per
| 0 |  | 0 |  | 0
| 117.3611 |  | 58.6806 |  | 4694.4444 |  | EACH | 2 | 1 | 80 | [6 empty] | EACH | 2 | 1 | 80 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | EACH | 10 | 5 | 4 | [6 empty] | EACH | 10 | 5 | 4 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 140.8333 |  | 70.4167 |  | 56.3333 |  | L.M. | 2.4 | 1.2 | 0.96 | [6 empty] | L.M. | 2.4 | 1.2 | 0.96 | per hour | per
| 352.0833 |  | 176.0417 |  | 140.8333 |  | L.M. | 6 | 3 | 2.4 | [6 empty] | L.M. | 6 | 3 | 2.4 | per hour | per
| 35.2083 |  | 17.6042 |  | 14.0833 |  | L.M. | 0.6 | 0.3 | 0.24 | [6 empty] | L.M. | 0.6 | 0.3 | 0.24 | per hour | per
| 35.2083 |  | 17.6042 |  | 14.0833 |  | L.M. | 0.6 | 0.3 | 0.24 | [6 empty] | L.M. | 0.6 | 0.3 | 0.24 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 1173.6111 |  | 58.6806 |  | 528.125 |  | TON | 20 | 1 | 9 | [6 empty] | TON | 20 | 1 | 9 | per hour | per
| 64.5486 |  | 32.2743 |  | 2581.9444 |  | S.M. | 1.1 | 0.55 | 44 | [6 empty] | S.M. | 1.1 | 0.55 | 44 | per hour | per
| 37.5556 |  | 18.7778 |  | 1525.6944 |  | S.M. | 0.64 | 0.32 | 26 | [6 empty] | S.M. | 0.64 | 0.32 | 26 | per hour | per
| 0 |  | 0 |  | 0
| 938.8889 |  | 469.4444 |  | 375.5556 |  | TON | 16 | 8 | 6.4 | [6 empty] | TON | 16 | 8 | 6.4 | per hour | per
| 50.4653 |  | 1760.4167 |  | 19.9514 |  | S.M. | 0.86 | 30 | 0.34 | [6 empty] | S.M. | 0.86 | 30 | 0.34 | per hour | per
| 3520.8333 |  | 0 |  | 1408.3333 |  | TON | 60 |  | 24 | [6 empty] | TON | 60 |  | 24 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 410.7639 |  | 205.3819 |  | 164.3056 |  | L.M. | 7 | 3.5 | 2.8 | [6 empty] | L.M. | 7 | 3.5 | 2.8 | per hour | per
| 704.1667 |  | 352.0833 |  | 281.6667 |  | S.M. | 12 | 6 | 4.8 | [6 empty] | S.M. | 12 | 6 | 4.8 | per hour | per
| 2112.5 |  | 1056.25 |  | 845 |  | S.M. | 36 | 18 | 14.4 | [6 empty] | S.M. | 36 | 18 | 14.4 | per hour | per
| 2816.6667 |  | 1408.3333 |  | 1126.6667 |  | EACH | 48 | 24 | 19.2 | [6 empty] | EACH | 48 | 24 | 19.2 | per hour | per
| 1408.3333 |  | 704.1667 |  | 563.3333 |  | EACH | 24 | 12 | 9.6 | [6 empty] | EACH | 24 | 12 | 9.6 | per hour | per
| 586.8056 |  | 293.4028 |  | 234.7222 |  | EACH | 10 | 5 | 4 | [6 empty] | EACH | 10 | 5 | 4 | per hour | per
| 938.8889 |  | 469.4444 |  | 375.5556 |  | EACH | 16 | 8 | 6.4 | [6 empty] | EACH | 16 | 8 | 6.4 | per hour | per
| 821.5278 |  | 428.3681 |  | 342.6944 |  | L.M. | 14 | 7.3 | 5.84 | [6 empty] | L.M. | 14 | 7.3 | 5.84 | per hour | per
| 2816.6667 |  | 1408.3333 |  | 1126.6667 |  | EACH | 48 | 24 | 19.2 | [6 empty] | EACH | 48 | 24 | 19.2 | per hour | per
| 938.8889 |  | 469.4444 |  | 375.5556 |  | EACH | 16 | 8 | 6.4 | [6 empty] | EACH | 16 | 8 | 6.4 | per hour | per
| 410.7639 |  | 205.3819 |  | 164.3056 |  | L.M. | 7 | 3.5 | 2.8 | [6 empty] | L.M. | 7 | 3.5 | 2.8 | per hour | per
| 0 |  | 0 |  | 0
| 0 |  | 0 |  | 0
| 78.6319 |  | 39.316 |  | 31.6875 |  | L.M. | 1.34 | 0.67 | 0.54 | [6 empty] | L.M. | 1.34 | 0.67 | 0.54 | per hour | per
| 23.4722 |  | 11.7361 |  | 9.3889 |  | L.M. | 0.4 | 0.2 | 0.16 | [6 empty] | L.M. | 0.4 | 0.2 | 0.16 | per hour | per
| 93.8889 |  | 46.9444 |  | 37.5556 |  | S.M. | 1.6 | 0.8 | 0.64 | [6 empty] | S.M. | 1.6 | 0.8 | 0.64 | per hour | per
| 195.9931 |  | 97.9965 |  | 49.2917 |  | S.M. | 3.34 | 1.67 | 0.84 | [6 empty] | S.M. | 3.34 | 1.67 | 0.84 | per hour | per
| 64.5486 |  | 32.2743 |  | 16.4306 |  | S.M. | 1.1 | 0.55 | 0.28 | [6 empty] | S.M. | 1.1 | 0.55 | 0.28 | per hour | per
| 58.6806 |  | 29.3403 |  | 14.6701 |  | L.M. | 1 | 0.5 | 0.25 | [6 empty] | L.M. | 1 | 0.5 | 0.25 | per hour | per
| 31.6875 |  | 15.8438 |  | 8.2153 |  | S.M. | 0.54 | 0.27 | 0.14 | [6 empty] | S.M. | 0.54 | 0.27 | 0.14 | per hour | per
| 187.7778 |  | 93.8889 |  | 46.9444 |  | CU.M. | 3.2 | 1.6 | 0.8 | [6 empty] | CU.M. | 3.2 | 1.6 | 0.8 | per hour | per
| 39.9028 |  | 19.9514 |  | 9.9757 |  | S.M. | 0.68 | 0.34 | 0.17 | [6 empty] | S.M. | 0.68 | 0.34 | 0.17 | per hour | per
| 645.4861 |  | 352.0833 |  | 1.7604 |  | L.M. | 11 | 6 | 0.03 | [6 empty] | L.M. | 11 | 6 | 0.03 | per hour | per
| 1290.9722 |  | 645.4861 |  | 3.5208 |  | L.M. | 22 | 11 | 0.06 | [6 empty] | L.M. | 22 | 11 | 0.06 | per hour | per
| 5692.0139 |  | 2875.3472 |  | 14.0833 |  | KG | 97 | 49 | 0.24 | [6 empty] | KG | 97 | 49 | 0.24 | per hour | per
| 213.5972 |  | 106.7986 |  | 53.3993 |  | CU.M. | 3.64 | 1.82 | 0.91 | [6 empty] | CU.M. | 3.64 | 1.82 | 0.91 | per hour | per

## EST. SHEET (hidden)
UNIT COST DERIVATION FORM
PROJECT TITLE:
LOCATION:
ITEM NO. |  | ITEM OF WORK:
ESTIMATED QUANTITIES: |  | UNIT:
A. | MATERIALS:
| DESCRIPTION | QTY. | UNIT | UNIT COST | AMOUNT
B. | LABOR/MANPOWER:
NO. | DESCRIPTION | NO. | NO.-DAYS | DAILY RATE | AMOUNT
C. | EQUIPMENT/TOOLS:
NO. | DESCRIPTION | NO. | NO.-DAYS | HOURLY RATE | AMOUNT
D | TOTAL DIRECT COST (A+B+C)
E | O.C.M. (% of D)
F | CONTRACTIRS PROFIT (% OF D)
G | VAT (10% Oof B+C)
H | TOTAL COST (D+E+F+G)
I | UNIT COST ( DIRECT)

## EQUIPMENT
PROBABLE OUTPUT OF HEAVY EQUIPMENT
| EQUIPMENT | PROBABLE OUTPUT
[6 empty] | Clearing & Grubbing | Lot Grading (Cut & Fill) m3 |  | Trench Excavation | Disposal of Unsuitable Materials m3-km |  | Road way Excavation (m3) |  | Embankment/Imported Backfill (m3) |  | Subgrade Preparation (m2) |  | Aggregate Sub-base Course (m3) |  | Aggregate Base Course (m3) |  | Bituminous Asphalt Pavement (MT) |  | Concrete Pavement (m3)
A.1 | EXCAVATOR 200
| Excavation | 45 | cu.m./hr. | 0.022222 | hr/m³
| Clearing & Grubbing | 150 | sq.m./hr | 0.0066667 | hr/m²
A.1 | DOZER 165 HP
| Cutting & Stockpiling | 30 | cu.m./hr. | 0.033333 | hr/m³
| Clearing & Grubbing | 300 | sq.m./hr | 0.0033333 | hr/m²
A.2 | DOZER D65P-7 |  |  |  |  | 300 | 30 | m3/hr |  |  |  | 29.41 | m3/hr
| Stripping | 200 | sq.m./hr | 0.005 | hr/m²
| Excavation | 25 | cu.m./hr. | 0.04 | hr/m³
| Quarrying | 50 | cu.m./hr. | 0.02 | hr/m³
| Pushing | 3 | sq.m./hr | 0.33333 | hr/m²
B.1 | LOADER -1.91 CU.M.
| Loading | 70 | cu.m./hr. | 0.014286 | hr/m³ |  |  |  |  | 125 | m3/hr
B.2 | LOADER 950 | [5 empty] | 232.55 | m3/hr
C. | DUMP TRUCK - 10 CU.M. | [5 empty] | 232.55 | m3/hr |  | 125 | m3/hr
| Hauling (dist. = 600M) | 90 | cu.m./hr. | 0.011111 | hr/m³
D. | GRADER- 130G | [5 empty] | 384.62 | m3/hr | [5 empty] | 142.86 | m3/hr | 769.23 | sq.m./hr | 76.92 | m3/hr | 115.38 | m3/hr
| 10 Passes | 700 | sq.m./hr | 0.0014286 | hr/m²
| Subgrading | 300 | sq.m./hr | 0.0033333 | hr/m²
| Spreading | 40 | cu.m./hr. | 0.025 | hr/m³
E.1 | ROLLER VIBRATORY | [16 empty] | 58.82 | m3/hr | 88.23 | m3/hr | 65 | MT/hr
| 10 Passes | 600 | sq.m./hr | 0.0016667 | hr/m²
SHEETS FOOT ROLLER
Static Rolling 12 passes-15m3 lift
| Vibratory Rolling-4 pases-15m3 lift | 135 | cu.m./hr. | 0.0074074 | hr/m³
No.3W Road Roller-static rolling
| 4 passes-15 m3 lift | 24 | cu.m./hr. | 0.041667 | hr/m³
Tractor Drawn Roller (1-d)
| Static Rolling 6 passes-20m3 lift | 240 | cu.m./hr. | 0.0041667 | hr/m³
Tandem Roller-static rolling
| 6 passes-20 m3 lift | 24 | cu.m./hr. | 0.041667 | hr/m³
E.2 | VIBRATORY COMPACTOR CA25D | [5 empty] | 303.03 | m3/hr | [5 empty] | 125 | m3/hr | 588.23 | sq.m./hr
G. | WATER TRUCK - 10 CU.M. | [5 empty] | 769.23 | m3/hr | [5 empty] | 333.33 | m3/hr | 1666.67 | sq.m./hr | 166.67 | m3/hr | 250 | m3/hr
| Watering | 1600 | sq.m./hr | 0.000625 | hr/m²
| ASPHALT PAVER | [20 empty] | 32.5 | MT/hr
| ASPHALT DISTRIBUTOR | SPRAYING PHALT | [19 empty] | 300 | SQ.M.
PLATE COMPACTOR
| Grave Bedding | 8 | cu.m./hr. | 0.125 | hr/m³
Concrete Vibrator:
| Vibrating Concrete | 40 | cu.m./hr. | 0.025 | hr/m³
[22 empty] | Asphalt prime coat, SS-1 (.042 drum/mt) | drums
Note:1MT of asphalt conc. Covers 8 m2
of pavement 2" thick or 0.43 m3 of asphalt
concrete
Coverage = 2.33 MT/CM
Bitumil = 0.70 ltr/sq, 200 ltr/drum

## BONUS DATA - STEEL ERECTION
A. | STRIPPING OF METAL FORMS
MANHOURS PER SQ. METER OF CONTACT AREA
WOOD SHORES 215 TO 316 FLOORS
|  | FORM HEIGHT | LOW | AVERAGE | HIGH
(METER)
|  | 3 TO 4 | 0.58 | 0.22 | 0.16
|  | 4 TO 5 | 0.59 | 0.23 | 0.16
|  | 5 TO 6 | 0.6 | 0.23 | 0.17
|  | 6 TO 7 | 0.61 | 0.24 | 0.17
|  | 7 TO 8 | 0.64 | 0.25 | 0.18
WOOD SHORES 368 TO 419 FLOORS
|  | 3 TO 4 | 0.6 | 0.23 | 0.17
|  | 4 TO 5 | 0.61 | 0.24 | 0.17
|  | 5 TO 6 | 0.64 | 0.25 | 0.18
|  | 6 TO 7 | 0.66 | 0.25 | 0.18
|  | 7 TO 8 | 0.68 | 0.26 | 0.19
| CREW: |  |  |  |  | TOOLS:
| 1 | CARPENTER LEAD MAN | 8 |  |  | ONE LOT CARPENTRY TOOLS
| 3 | CARPENTERS | 24 |  |  | 8 | TOOLS HOUR
| 6 | HELPERS | 48
| 10 | MANDAYS | 80 | MANHOURS
B. | STEEL ERECTION FOR MULTI STOREY BUILDING FRAME
PREFAB SECTIONS, HIGHLY MECHANIZED OPERATION
MANHOURS & EQUIPMENTHOUR PER TON ERECTED:
|  |  | MAN-HOURS |  |  |  | EQUIPMENT-HOURS
|  |  | LOW | AVERAGE | HIGH |  | LOW | AVERAGE | HIGH
| MEDIUM FRAME |  | 36 | 13.85 | 10 |  | 7 | 2.69 | 1.94
| HEAVY FRAME |  | 32.73 | 12.63 | 9.11 |  | 6.36 | 2.46 | 1.77
| STEEL JOIST |  | 40 | 15.37 | 11.08 |  | 7.78 | 2.98 | 2.15
| CREW: |  |  |  |  | TOOLS:
| 1 | LEAD MAN | 8 |  |  | 0.5 | TOWER CRANE |  |  | 4
| 4 | RIGGERS | 32 |  |  | 2 | WELDING TRANSFORMER |  |  | 16
| 4 | FITTERS | 32 |  |  | 1 | LOT TOOLS |  |  | 8
| 2 | WELDERS | 16 |  |  | 3.5 |  |  |  | 28 | TOOL HOURS
| 1 | CRANE OPERATOR | 8
| 6 | HELPERS | 48
| 18 | MANDAYS | 144 | MANHOURS
MATERIALS : A36 WELDED CONNECTION
C. | STEEL ERECTION FOR COMMERCIAL AND MILL BUILDING FRAME
PREFAB SECTIONS, HIGHLY MECHANIZED OPERATION
MANHOURS & EQUIPMENTHOUR PER TON ERECTED:
|  |  | MAN-HOURS |  |  |  | EQUIPMENT-HOURS
|  |  | LOW | AVERAGE | HIGH |  | LOW | AVERAGE | HIGH
COMMERCIAL TYPE BUILDING:
| LIGHT FRAME |  | 46.67 | 18.06 | 13.02 |  | 18.33 | 7.1 | 5.12
| MEDIUM FRAME |  | 40 | 15.56 | 11.2 |  | 15.71 | 6.11 | 4.4
| HEAVY FRAME |  | 35 | 13.33 | 9.66 |  | 13.75 | 5.24 | 3.79
| STEEL JOIST |  | 43.08 | 16.47 | 11.91 |  | 16.92 | 6.47 | 4.68
MILL TYPE BUILDING:
| LIGHT FRAME |  | 35 | 13.33 | 9.66 |  | 13.75 | 5.24 | 3.79
| MEDIUM FRAME |  | 31.11 | 11.91 | 8.62 |  | 12.22 | 4.68 | 3.38
| HEAVY FRAME |  | 35 | 10.77 | 7.78 |  | 13.75 | 4.23 | 3.06
| STEEL JOIST |  | 32.94 | 12.27 | 9.18 |  | 12.94 | 5 | 3.61
| CREW: |  |  |  |  | TOOLS:
| 1 | LEAD MAN | 8 |  |  | 0.5 | 20 TON TOWER CRANE |  |  | 4
| 2 | RIGGERS | 16 |  |  | 2 | WELDING TRANSFORMER |  |  | 16
| 4 | FITTERS | 32 |  |  | 2 | CUTTING OUTFIT |  |  | 16
| 2 | WELDERS | 16 |  |  | 1 | LOT TOOLS |  |  | 8
| 1 | CRANE OPERATOR | 8 |  |  | 5.5 | EQPT. DAYS |  |  | 44 | EQPT. HOURS
| 4 | HELPERS | 32
| 14 | MANDAYS | 112 | MANHOURS
MATERIALS : A36 WELDED CONNECTION